## Effective Greenfield
1. Effective Greenfield 2023/24
[23 empty] | Short Term |  |  | Medium Term |  |  | Long Term
Site_reference | LDP2_reference | Year site added | Site area (ha) | Site address | Easting | Northing | Site type | Site status | Owner/Developer | Tenure type | Planning Application Reference | Last planning approval date | Date completed / expired | Greenfield / Brownfield | Self build | Windfall Site | Site capacity | No of houses | No of flats | Plots complete in survey year 23/24 | Total completions | Units to build | Year 24/25 | Year 25/26 | Year 26/27 | Year 27/28 | Year 28/29 | Year 29/30 | Year 30/31 | Year 31/32 | Year 32/33 | Year 33/34 | Later Years | Total Programmed
200356A |  | 2016-03-11 | 19.3417 | WESTERN GATEWAY, SOUTH GRAY | 334131 | 731821 | Effective | Under Construction | SPRINGFIELD | Private | 15/00121/FULM, 16/00370/FULL, 16/01012/MDPO, 17/00938/FULL, 18/00539/FULL | 2018-11-06 |  | Greenfield | No | Yes | 341 | 146 | 58 | 0 | 201 | 140 | 0 | 45 | 45 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140
200408 |  | 2015-06-03 | 24.3312 | WESTERN GATEWAY, SWALLOW | 334038 | 731320 | Effective | Under Construction | SPRINGFIELD | Private | 14/00205/FULM, 16/01023/FULL, 17/00409/MDPO, 23/00168/FULL | 2017-07-19 |  | Greenfield | No | No | 230 | 0 | 0 | 26 | 133 | 97 | 42 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 97
200738 |  | 2016-06-17 | 7.8207 | DUNDEE WESTERN LIFF PHASE 2 | 334379 | 732314 | Effective | Under Construction | SPRINGFIELD | Private | 15/00410/FULM, 18/00992/FULL | 2019-02-06 |  | Greenfield | No | Yes | 100 | 100 | 0 | 0 | 0 | 100 | 0 | 25 | 25 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 100
201423 |  | 2016-07-20 | 1.0007 | PITKERRO MILL | 345078 | 733464 | Effective | Under Construction | SOUTH TAY LTD | Private | 16/00394/FULL | 2016-07-20 |  | Greenfield | No | Yes | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
201821 | H42 | 2018-04-01 | 3.2797 | WESTERN GATEWAY, LIFF | 334219 | 732498 | Effective | Allocated in LDP | NHS | Private |  |  |  | Greenfield | No | No | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 30
201822 | H43 | 2018-04-01 | 13.4423 | DYKES OF GRAY, NORTH EAST | 334471 | 732016 | Effective | Allocated in LDP | SPRINGFIELD | Private |  |  |  | Greenfield | No | No | 215 | 0 | 0 | 0 | 0 | 215 | 0 | 0 | 30 | 30 | 36 | 36 | 36 | 36 | 11 | 0 | 0 | 215
201823 | H44 | 2018-04-01 | 6.2216 | BALDRAGON FARM | 337401 | 734790 | Effective | Under Construction | AVANT HOMES | Private | 19/00707/FULM, 20/00771/FULL | 2021-04-09 |  | Greenfield | No | No | 120 | 120 | 0 | 16 | 46 | 74 | 37 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74
201824B | H45 | 2021-05-21 | 7.4872 | BALLUMBIE ROAD, LAND TO EAST OF - PHASE 2 | 344607 | 733962 | Effective | Planning Consent | STEWART MILNE | Private | 20/00423/FULM | 2021-05-21 |  | Greenfield | No | No | 150 | 150 | 0 | 0 | 0 | 150 | 18 | 36 | 36 | 36 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 150
201829 | H41 | 2018-01-11 | 21.9833 | DYKES OF GRAY, NORTH WEST | 333717 | 731646 | Effective | Allocated in LDP | SPRINGFIELD | Private |  |  |  | Greenfield | No | No | 250 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 24 | 48 | 48 | 48 | 48 | 0 | 34 | 250
201830 | H46 | 2018-06-25 | 15.8973 | ARBROATH ROAD, LINLATHEN | 346394 | 733242 | Effective | Under Construction | KIRKWOOD HOMES | Private | 18/00115/FULM, 19/00799/FULM, 21/00322/FULL, 21/00376/FULL, 21/00677/FULL, 21/00713/FULL | 2021-07-01 |  | Greenfield | No | No | 250 | 250 | 0 | 39 | 185 | 65 | 33 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65
[17 empty] | 1692 | 772 | 58 | 81 | 565 | 1127 | 136 | 175 | 136 | 141 | 164 | 114 | 84 | 84 | 59 | 0 | 34 | 1127

## Effective Brownfield
2. Effective Brownfield 2023/24
[23 empty] | Short Term |  |  | Medium Term |  |  | Long Term
Site_reference | LDP2_reference | Year site added | Site area (ha) | Site address | Easting | Northing | Site type | Site status | Owner/Developer | Tenure type | Planning Application Reference | Last planning approval date | Date completed / expired | Greenfield / Brownfield | Self build | Windfall Site | Site capacity | No of houses | No of flats | Plots complete in survey year 23/24 | Total completions | Units to build | Year 24/25 | Year 25/26 | Year 26/27 | Year 27/28 | Year 28/29 | Year 29/30 | Year 30/31 | Year 31/32 | Year 32/33 | Year 33/34 | Later Years | Total Programmed
200347 |  | 2013-12-17 | 1.0067 | MONIFIETH ROAD, ARMITSTEAD | 347412 | 731148 | Effective | Under Construction | H & H PROPERTIES LTD | Private | 13/00642/FULL, 16/00179/FULL, 21/00904/FULL | 2022-04-15 |  | Brownfield | No | No | 26 | 3 | 23 | 0 | 0 | 26 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26
200504D | H32 | 2020-10-22 | 1.8237 | ABERLADY CRESCENT PHASE 3B/4 | 343953 | 733534 | Effective | Under Construction | DJ LAING | Private | 20/00121/FULL, 22/00657/FULL | 2023-02-10 |  | Brownfield | No | No | 34 | 32 | 0 | 4 | 31 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
200611 |  | 2007-06-05 | 1.6776 | RIVERSIDE DRIVE, FORMER HOMEBASE SITE | 339577 | 729422 | Effective | Under Construction | H & H PROPERTIES LTD | Private | 05/00770/FUL | 2007-06-05 |  | Brownfield | No | Yes | 135 | 0 | 135 | 1 | 85 | 50 | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50
200909 | H11 | 2009-04-01 | 1.2778 | EAST SCHOOL ROAD, FORMER DOWNFIELD PS | 338919 | 733132 | Effective | Under Construction | H & H PROPERTIES LTD | Private | 20/00076/FULL | 2020-11-18 |  | Brownfield | No | No | 23 | 23 | 0 | 0 | 0 | 23 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23
200911 | H08 | 2019-06-24 | 1.5846 | ST LEONARD PLACE, FORMER MACALPINE PS | 338134 | 733812 | Effective | Under Construction | H & H PROPERTIES LTD | Private | 17/00420/FULL, 21/00406/FULL | 2021-12-15 |  | Brownfield | No | No | 33 | 33 | 0 | 12 | 32 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
200913 | H09 | 2009-04-01 | 4.0249 | RANNOCH ROAD, FORMER LAWSIDE ACADEMY | 338363 | 733094 | Effective | Allocated in LDP | DUNDEE CITY COUNCIL | Private |  |  |  | Brownfield | No | No | 70 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 20 | 20 | 30 | 0 | 0 | 0 | 0 | 70
201008 | H31 | 2010-04-01 | 1.3369 | LOTHIAN CRESCENT, BOWLING GREEN EAST | 343913 | 733373 | Effective | Allocated in LDP | DUNDEE CITY COUNCIL | Private |  |  |  | Brownfield | No | No | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
201010 | H28 | 2010-04-01 | 3.7588 | TRANENT GROVE | 343320 | 733503 | Effective | Allocated in LDP | DUNDEE CITY COUNCIL | Private | 22/00461/FULL | 2022-12-16 |  | Brownfield | No | No | 53 | 0 | 0 | 0 | 0 | 53 | 0 | 0 | 22 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53
201010A | H28 | 2022-12-16 | 1.3436 | TRANENT GROVE | 343303 | 733461 | Effective | Planning Consent | DISCOVERY HOMES LTD | Private | 22/00461/FULL | 2022-12-16 |  | Brownfield | No | No | 17 | 17 | 0 | 0 | 0 | 17 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17
201011A | H27 | 2023-09-13 | 1.2007 | Whitfield Drive, South, Site Of Whitfield Primary School | 343204 | 733328 | Effective | Planning Consent | ANGUS HA | Housing Association | 19/00716/FULL | 2023-09-13 |  | Brownfield | No |  | 18 | 10 | 8 | 0 | 0 | 18 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
201011B | H27 | 2023-09-13 | 1.1547 | Whitfield Drive, North, Site Of Whitfield Primary School | 343234 | 733380 | Effective | Planning Consent | GEORGE MARTIN | Private | 19/00776/FULL | 2023-09-13 |  | Brownfield | No | No | 30 | 30 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 30
201012 | H25 | 2010-04-01 | 1.8274 | LOTHIAN CRESCENT, FORMER WHITFIELD SHOPPING CENTRE | 343056 | 733375 | Effective | Allocated in LDP | DUNDEE CITY COUNCIL | Private/RSL |  |  |  | Brownfield | No | No | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
201102 |  | 2010-12-21 | 0.07577 | DURA STREET, 3 | 340858 | 731298 | Effective | Planning Consent | WHITTET LTD | Private | 10/00676/FULL, 13/00824/FULL, 17/00014/FULL, 20/00018/FULL, 23/00153/FULL | 2023-06-29 |  | Brownfield | No | Yes | 8 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
201106 |  | 2011-04-01 | 0.035264 | SEAGATE/TRADES LANE | 340548 | 730518 | Effective | Under Construction | HILLCREST HA | RSL | 16/01058/FULL | 2017-08-21 |  | Brownfield | No | Yes | 28 | 0 | 28 | 0 | 0 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
201108 |  | 2011-04-01 | 3.587 | DERBY STREET, FORMER MULTIS | 339832 | 731556 | Effective | Under Construction | DCC/HILLCREST | DCC/RSL | 16/00806/FULM, 17/00799/FULL | 2017-12-11 |  | Brownfield | No | Yes | 162 | 39 | 123 | 111 | 136 | 26 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26
201109 | H17 | 2011-04-01 | 23.9694 | CENTRAL WATERFRONT * | 340509 | 729995 | Effective | Allocated in LDP | DUNDEE CITY COUNCIL | Mixed | 17/00113/FULM, 18/00400/FULL, 20/00399/FULL | 2020-10-16 |  | Brownfield | No | No | 276 | 0 | 276 | 0 | 0 | 276 | 0 | 0 | 0 | 0 | 0 | 60 | 70 | 70 | 76 | 0 | 0 | 276
201109A | H17 | 2017-06-23 | 0.7231 | CENTRAL WATERFRONT - SITE 6 * | 340454 | 729970 | Effective | Under Construction | DUNDEE CITY COUNCIL | Private | 17/00113/FULM, 18/00400/FULL | 2018-08-17 |  | Brownfield | No | Yes | 99 | 0 | 99 | 0 | 0 | 99 | 0 | 0 | 0 | 50 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 99
201109B | H17 | 2020-10-16 | 0.37882 | DOCK STREET, HARBOUR CHAMBERS / CUSTOMS HOUSE | 340688 | 730304 | Effective | Under Construction | ALICYDON LTD | Private | 20/00399/FULL | 2020-10-16 |  | Brownfield | No | Yes | 49 | 0 | 49 | 0 | 0 | 49 | 0 | 0 | 0 | 20 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 49
201110 | H23 | 2011-04-01 | 1.4577 | BALLOCHMYLE DRIVE, FORMER MOSSGIEL PSC PHASE 2 | 341769 | 732646 | Effective | Allocated in LDP | DUNDEE CITY COUNCIL | RSL |  |  |  | Brownfield | No | No | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
201213 | H22 | 2012-04-01 | 0.57888 | HEBRIDES DRIVE SOUTH EAST, MOM-PHASE 4) | 341518 | 733254 | Effective | Under Construction | HOME SCOTLAND | RSL | 18/00974/FULL, 23/00059/FULL | 2024-01-09 |  | Brownfield | No | No | 31 | 7 | 24 | 0 | 0 | 31 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31
201214 | H21 | 2012-04-01 | 0.4467 | HEBRIDES DRIVE NORTH EAST, MOM-PHASE 4 | 341531 | 733473 | Effective | Under Construction | HOME SCOTLAND | RSL | 18/00974/FULL, 23/00059/FULL | 2024-01-09 |  | Brownfield | No | No | 17 | 7 | 10 | 0 | 0 | 17 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17
201221 | H20 | 2012-04-01 | 0.63833 | HEBRIDES DRIVE WEST, MOM-PHASE 4 | 341048 | 733472 | Effective | Allocated in LDP | DUNDEE CITY COUNCIL | Private |  |  |  | Brownfield | No | No | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10
201414 | H10 | 2014-04-01 | 0.82733 | LAUDERDALE AVENUE | 338598 | 733531 | Effective | Under Construction | INVERTAY HOMES | Private | 18/00463/FULL | 2018-09-14 |  | Brownfield | No | No | 27 | 27 | 0 | 2 | 26 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
201415 | H12 | 2014-04-01 | 0.66612 | KIRKTON ROAD, FORMER ST COLUMBAS PS | 339075 | 733403 | Effective | Under Construction | H & H PROPERTIES LTD | Private | 17/00417/FULL | 2020-11-18 |  | Brownfield | No | No | 21 | 21 | 0 | 13 | 13 | 8 | 10 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21
201417 | H05 | 2014-04-01 | 1.7818 | SOUTH ROAD, FORMER LOCHEE PS | 337330 | 731477 | Effective | Planning Consent | DUNDEE CITY COUNCIL | Private | 22/00402/FULL | 2023-11-01 |  | Brownfield | No | No | 39 | 39 | 0 | 0 | 0 | 39 | 0 | 30 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39
201510 | H06 | 2015-04-01 | 6.1424 | LOCHEE DISTRICT CENTRE | 337857 | 731572 | Effective | Allocated in LDP | HILLCREST HA | RSL | 13/00678/FULL, 15/00079/FULL, 19/00738/FULL | 2020-01-27 |  | Brownfield | No | No | 40 | 0 | 0 | 0 | 0 | 40 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40
201813 | H16 | 2018-04-01 | 0.61367 | MAXWELLTOWN, FORMER MULTIS | 340172 | 731036 | Effective | Allocated in LDP | DUNDEE CITY COUNCIL | TBC |  |  |  | Brownfield | No | No | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 30
201814 | H34 | 2018-04-01 | 1.6697 | ETIVE GARDENS, FORMER GOWRIEHILL PS | 335665 | 731239 | Effective | Allocated in LDP | DUNDEE CITY COUNCIL | RSL |  |  |  | Brownfield | No | No | 35 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35
201815 | H35 | 2018-04-01 | 1.9738 | DENOON TERRACE, FORMER HILLSIDE PS | 336897 | 731187 | Effective | Allocated in LDP | DUNDEE CITY COUNCIL | TBC |  |  |  | Brownfield | No | No | 45 | 0 | 0 | 0 | 0 | 45 | 0 | 15 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45
201816 | H36 | 2018-04-01 | 0.36187 | HIGH STREET, LOCHEE, FORMER ST MARYS INFANT SCHOOL | 337998 | 731337 | Effective | Allocated in LDP | DUNDEE CITY COUNCIL | TBC |  |  |  | Brownfield | No | No | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
201817 | H37 | 2018-04-01 | 4.926 | BURN STREET, FORMER BALDRAGON ACADEMY | 339111 | 733973 | Effective | Allocated in LDP | DUNDEE CITY COUNCIL | TBC |  |  |  | Brownfield | No | No | 70 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70
201825 | H14 | 2018-04-01 | 2.1768 | GREENMARKET, FORMER RAILYARDS * | 339467 | 729510 | Effective | Allocated in LDP | SCOTTISH ENTERPRISE | TBC |  |  |  | Brownfield | No | No | 110 | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 50 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 110
201826C | H29 | 2022-06-13 | 1.9422 | SUMMERFIELD AVENUE AT SUMMERFIELD GARDENS, LAND TO WEST | 343614 | 733089 | Effective | Under Construction | INVERTAY HOMES | Private | 21/00736/FULL | 2022-06-13 |  | Brownfield | No | No | 34 | 34 | 0 | 0 | 0 | 34 | 0 | 15 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34
201826D | H29 | 2023-03-30 | 0.36088 | SUMMERFIELD AVENUE AT SUMMERFIELD GARDENS, LAND TO WEST | 343680 | 733153 | Effective | Under Construction | INVERTAY HOMES | Private | 22/00148/FULL | 2023-03-30 |  | Brownfield | No | No | 8 | 8 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
201827 | H33 | 2018-04-01 | 8.4241 | DRUMGEITH ROAD, KELLYFIELD | 344237 | 733239 | Effective | Allocated in LDP | DUNDEE CITY COUNCIL | TBC |  |  |  | Brownfield | No | No | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 30 | 30 | 40 | 0 | 0 | 0 | 0 | 0 | 100
201902 |  | 2018-07-16 | 0.85219 | COLDSIDE ROAD, LAND SOUTH OF | 339507 | 731945 | Effective | Under Construction | CALEDONIA HA | RSL | 17/00933/FULL | 2018-07-16 |  | Brownfield | No | Yes | 30 | 18 | 12 | 20 | 20 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
201906 |  | 2018-09-25 | 0.14061 | LANGLANDS STREET | 341037 | 731374 | Effective | Under Construction | HILLCREST HA | RSL | 18/00500/FULL | 2018-09-25 |  | Brownfield | No | Yes | 16 | 0 | 16 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
201908 |  | 2018-12-20 | 0.57494 | THORTER LOAN/SOUTH VICTORIA DOCK ROAD | 340968 | 730232 | Effective | Under Construction | HILLCREST HA | RSL | 18/00387/FULM | 2018-12-20 |  | Brownfield | No | Yes | 119 | 0 | 119 | 66 | 66 | 53 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53
201910 |  | 2018-12-14 | 0.28532 | GUTHRIE STREET, THE OLD MILL | 339735 | 730377 | Effective | Under Construction | RAMSAY PROPERTIES LTD | Private | 17/00134/FULL | 2018-12-14 |  | Brownfield | No | Yes | 17 | 0 | 17 | 0 | 0 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17
201912 |  | 2019-04-09 | 3.9484 | ELLENGOWAN DRIVE | 341769 | 731105 | Effective | Under Construction | HILLCREST HA | RSL | 18/00487/FULM | 2019-04-09 |  | Brownfield | No | Yes | 130 | 39 | 91 | 8 | 70 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60
201913 |  | 2018-06-21 | 0.18826 | CANDLE LANE, 9-11 | 340603 | 730390 | Effective | Under Construction | HILLCREST HA | RSL | 18/00016/FULL | 2018-06-21 |  | Brownfield | No | Yes | 24 | 0 | 24 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
202003 |  | 2019-04-17 | 0.068309 | MURRAYGATE, 11-23 | 340422 | 730416 | Effective | Under Construction | HILLCREST HA | RSL | 18/01012/FULL | 2019-04-17 |  | Brownfield | No | Yes | 31 | 0 | 31 | 0 | 0 | 31 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31
202009 |  | 2019-09-18 | 0.91844 | MORGAN STREET, TAYBANK WORKS PH 2 | 341351 | 731255 | Effective | Planning Consent | CALEDONIA HA | RSL | 19/00227/FULL, 20/00039/FULL, 20/00306/FULL, 21/00326/FULL | 2021-11-19 |  | Brownfield | No | Yes | 37 | 21 | 16 | 0 | 0 | 37 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37
202012 |  | 2019-12-18 | 2.8817 | KINGSWAY EAST, FORMER STEWART HOUSE | 342852 | 731829 | Effective | Under Construction | PERSIMMON HOMES | Private | 19/00687/FULM, 23/00449/FULL | 2023-09-07 |  | Brownfield | No | Yes | 71 | 71 | 0 | 0 | 0 | 71 | 36 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71
202013 |  | 2020-01-23 | 0.21362 | BUTTARS LOAN, SITE TO THE EAST | 336795 | 731616 | Effective | Under Construction | GREEN PADS LTD | Private | 19/00246/FULL | 2020-01-23 |  | Brownfield | No | Yes | 8 | 8 | 0 | 0 | 0 | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
202022 |  | 2020-05-01 | 0.31929 | EAST SCHOOL ROAD, DOWNFIELD HOUSE | 339035 | 733033 | Effective | Under Construction | ABERKELL DEVELOPMENTS | Private | 19/00830/FULL, 22/0024/NMV | 2020-05-01 |  | Brownfield | No | Yes | 14 | 2 | 12 | 2 | 4 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
202024 |  | 2020-05-21 | 1.02 | PITKERRO ROAD, NORTH OF, LONGHAUGH ROAD, EAST OF | 342795 | 732954 | Effective | Under Construction | LONGHAUGH DEVELOPMENTS LTD | Private | 19/00063/FULL, | 2020-05-21 |  | Brownfield | No | Yes | 14 | 14 | 0 | 4 | 12 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
202030 |  | 2020-07-30 | 0.12902 | GELLATLY STREET, 3 | 340610 | 730351 | Effective | Under Construction | MCGILL (DOCK STREET) LTD | Private | 19/00502/FULL, 21/00215/FULL | 2021-12-07 |  | Brownfield | No | Yes | 49 | 0 | 49 | 0 | 0 | 49 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49
202032B |  | 2020-09-01 | 0.20792 | FAIRFIELD ROAD, 10 | 344602 | 731449 | Effective | Under Construction | WEST DEVELOPMENTS (SCOTLAND) LTD | Private | 20/00160/FULL, 21/00651/FULL, | 2021-11-11 |  | Brownfield | No | Yes | 4 | 0 | 4 | 1 | 1 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
202051 |  | 2020-07-10 | 0.73952 | PITKERRO ROAD, 114-116, LAND AT | 342347 | 732643 | Effective | Under Construction | ANGUS HA | RSL | 20/00052/FULL, 20/00777/FULL | 2021-02-02 |  | Brownfield | No | Yes | 21 | 13 | 8 | 0 | 0 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21
202053 |  | 2021-02-18 | 2.1982 | MURRAYFIELD PLACE, MURRAYFIELD DRIVE, WHITFIELD AVENUE | 343109 | 732956 | Effective | Planning Consent | DUNDEE CITY COUNCIL | Local Authority | 20/00064/FULL, 22/00239/FULL | 2022-07-25 |  | Brownfield | No | Yes | 42 | 10 | 32 | 0 | 0 | 42 | 0 | 22 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42
202061B |  | 2020-10-22 | 0.22415 | DALKEITH ROAD, 69 | 341712 | 731577 | Effective | Under Construction | MARVEND LTD | Private | 19/00026/FULL, 20/00142/FULL | 2020-10-22 |  | Brownfield | No | Yes | 4 | 1 | 3 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
202065 |  | 2020-11-18 | 0.26635 | DALKEITH ROAD, 57 | 341769 | 731399 | Effective | Under Construction | PRIVATE | Private | 20/00209/FULL | 2020-11-18 |  | Brownfield | No | Yes | 8 | 8 | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
202066 |  | 2020-12-17 | 0.65834 | LIFF PLACE, BROWNHILL PLACE. SITES 1 & 2 | 336499 | 732119 | Effective | Under Construction | BLACKWOOD HOMES & CARE | RSL | 20/00247/FULL | 2020-12-17 |  | Brownfield | No | Yes | 23 | 3 | 20 | 0 | 0 | 23 | 10 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23
202067 |  | 2020-12-17 | 0.91009 | GOURDIE PLACE, GOURDIE CRESCENT, LAND AT. SITES 3 & 4 | 336236 | 731913 | Effective | Under Construction | BLACKWOOD HOMES & CARE | RSL | 20/00248/FULL | 2020-12-17 |  | Brownfield | No | Yes | 22 | 10 | 12 | 0 | 0 | 22 | 10 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22
202068 |  | 2020-12-17 | 0.48089 | BUTTARS ROAD, LAND TO SOUTH. SITES 5 & 6 | 336603 | 731958 | Effective | Under Construction | BLACKWOOD HOMES & CARE | RSL | 20/00249/FULL | 2020-12-17 |  | Brownfield | No | Yes | 9 | 3 | 6 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
202104 |  | 2021-06-16 | 1.3421 | ROSEBANK ROAD, LAND AT FORMER ROSEBANK PRIMARY SCHOOL | 339990 | 730905 | Effective | Under Construction | DISCOVERY HOMES LTD | Private | 21/00011/FULL | 2021-06-16 |  | Brownfield | No | Yes | 40 | 40 | 0 | 8 | 8 | 32 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
202105F |  | 2021-11-01 | 0.010331 | REFORM STREET, 51, MF SPACE | 340245 | 730375 | Effective | Planning Consent | PRIVATE | Private | 21/00719/FULL | 2021-11-18 |  | Brownfield | No | Yes | 4 | 0 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
202106 |  | 2021-08-01 | 0.2112 | COUPAR ANGUS ROAD, 40, SITE OF FORMER HOTEL | 337386 | 732179 | Effective | Under Construction | REDWOOD BIRKHILL LIMITED | RSL | 20/00591/FULL | 2021-08-17 |  | Brownfield | No | Yes | 18 | 0 | 18 | 0 | 0 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
202107 |  | 2021-12-01 | 1.1481 | PERTH ROAD, 329, FERNBRAE HOSPITAL | 337615 | 729923 | Effective | Planning Consent | S1 WEST LTD | Private | 21/00604/FULL | 2021-12-15 |  | Brownfield | No | Yes | 23 | 6 | 17 | 0 | 0 | 22 | 0 | 10 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22
202108 |  | 2021-04-21 | 0.25114 | MAGDALEN YARD ROAD, LAND AT FORMER TAY ROPE WORKS | 339151 | 729525 | Effective | Under Construction | F & H DEVELOPMENTS | Private | 19/00297/FULL | 2021-04-21 |  | Brownfield | No | Yes | 9 | 5 | 4 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
202115 |  | 2021-11-18 | 0.03 | WHITEHALL CRESCENT, 3 | 340357 | 730131 | Effective | Under Construction | JOUP PROPERTY LTD | Private | 21/00636/FULL | 2021-11-18 |  | Brownfield | No | Yes | 14 | 0 | 14 | 0 | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
202201 |  | 2022-02-09 | 0.1765 | BLACKNESS ROAD, 247, LAND TO EAST OF | 338564 | 730306 | Effective | Planning Consent | DUNDEE CITY COUNCIL | RSL | 21/00525/FULL | 2022-02-09 |  | Brownfield | No | Yes | 24 | 0 | 24 | 0 | 0 | 24 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
202202 |  | 2022-03-16 | 2.1001 | BALLINDEAN ROAD, SITE OF FORMER FACTORY | 343400 | 732158 | Effective | Under Construction | CULLROSS LTD/CALEDONIA HA/BOC LTD | Mixed | 21/00602/FULM | 2022-03-16 |  | Brownfield | No | Yes | 67 | 43 | 24 | 0 | 0 | 67 | 55 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67
202203 |  | 2022-03-17 | 0.039053 | NICOLL STREET, 6 | 339986 | 730411 | Effective | Planning Consent | PRIVATE | Private | 20/00598/FULL | 2022-03-17 |  | Brownfield | No | Yes | 10 | 0 | 10 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
202204 |  | 2022-02-17 | 6.3067 | MAINS LOAN, 32 - 34, SITE OF FORMER JAMES KEILLER BUILDINGS | 340952 | 732266 | Effective | Under Construction | BARRATT NORTH SCOTLAND/MARKETGAIT DEVELOPMENTS | Private | 20/00098/FULM | 2022-02-17 |  | Brownfield | No | Yes | 223 | 167 | 56 | 28 | 28 | 195 | 52 | 52 | 52 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196
202205 |  | 2022-03-17 | 0.57137 | BURNSIDE STREET, 55 | 338192 | 731432 | Effective | Planning Consent | HILLCREST HA | RSL | 21/00857/FULM | 2022-03-17 |  | Brownfield | No | Yes | 54 | 0 | 54 | 0 | 0 | 54 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54
202206 |  | 2021-05-21 | 0.29665 | BROWNHILL PLACE, BROWNHILL STREET. SITE 7 | 336681 | 732054 | Effective | Under Construction | BLACKWOOD HOMES & CARE | RSL | 20/00250/FULL | 2021-05-21 |  | Brownfield | No | Yes | 12 | 0 | 12 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
202303 |  | 2022-09-27 | 0.15991 | GUTHRIE STREET, 9 | 339644 | 730319 | Effective | Planning Consent | PRIVATE | Private | 21/00296/FULL | 2022-09-27 |  | Brownfield | No | Yes | 18 | 0 | 18 | 0 | 0 | 18 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
202308 |  | 2022-12-22 | 0.30628 | ELLIOT ROAD, MAINS OF BALGAY | 337381 | 730420 | Effective | Planning Consent | PRIVATE | Private | 22/00563/FULL | 2022-12-22 |  | Brownfield | No | Yes | 5 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
202309 |  | 2022-12-22 | 0.02379 | HILLTOWN, 114, MOSQUE | 340168 | 730930 | Effective | Planning Consent | PRIVATE | Private | 22/00699/FULL | 2022-12-22 |  | Brownfield | No | Yes | 5 | 0 | 5 | 0 | 0 | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
202310 |  | 2023-02-10 | 0.045363 | CANDLE LANE, 3-7 | 340567 | 730409 | Effective | Planning Consent | MURRAYFIELD PROPERTIES LTD | Private | 20/00739/FULL | 2023-02-10 |  | Brownfield | No | Yes | 8 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
202319 |  | 2023-08-10 | 0.21219 | DONALDS LANE, SITE OF FORMER 6 | 336880 | 731887 | Effective | Planning Consent | H & H PROPERTIES LTD | Private | 22/00376/FULL | 2023-08-10 |  | Brownfield | No | Yes | 4 | 4 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
202320 |  | 2023-08-10 | 0.06744 | TANNADICE STREET, 14-22 | 340666 | 731666 | Effective | Planning Consent | PRIVATE | Private | 23/00362/PPPL | 2023-08-10 |  | Brownfield | No | Yes | 10 | 0 | 10 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
202322 |  | 2023-10-12 | 0.2027 | KINGHORNE ROAD, 119A, THE HIGH KIRK | 339491 | 731290 | Effective | Planning Consent | DAVID GRAY CONSTRUCTION LTD | Private | 23/00389/FULL | 2023-10-12 |  | Brownfield | No | Yes | 8 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
202324 |  | 2023-11-07 | 0.15234 | DICKSON AVENUE, THE ROCK | 336124 | 731003 | Effective | Planning Consent | ROCK DEVELOPMENTS (SCOTLAND) LTD | Private | 23/00510/FULL | 2023-11-07 |  | Brownfield | No | Yes | 16 | 0 | 16 | 0 | 0 | 16 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
202401 |  | 2024-01-10 | 0.2397 | NETHERGATE, 172, CAIRD REST | 339852 | 729813 | Effective | Planning Consent | PRIVATE | Private | 23/00451/FULL | 2024-01-10 |  | Brownfield | No | Yes | 5 | 0 | 5 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
[17 empty] | 3048 | 821 | 1562 | 280 | 532 | 2515 | 599 | 535 | 445 | 341 | 233 | 120 | 100 | 70 | 76 | 0 | 10 | 2529
67
94
111
8

## Constrained
3. Constrained 2023/24
Site_reference | LDP2 reference | Year site added | Site area (ha) | Site address | Easting | Northing | Site type | Site status | Owner/Developer | Tenure type | Planning Application Reference | Last planning approval date | Date completed / expired | Greenfield / Brownfield | Self build | Windfall Site | Site capacity | No of houses | No of flats | Plots complete in survey year 23/24 | Total completions | Units to build | Year 23/24 | Year 24/25 | Year 25/26 | Year 26/27 | Year 27/28 | Year 28/29 | Year 29/30 | Year 30/31 | Year 31/32 | Year 32/33 | Year 33/34 | Later Years | Total Programmed
200321 | H13 | 2003-04-01 | 1.2498 | QUEEN VICTORIA WORKS | 339248 | 730423 | Constrained | Constrained | PRIVATE | Private |  |  |  | Brownfield | No | No | 50 | 50 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200353 | H26 | 2003-04-01 | 0.83453 | LOTHIAN CRESCENT | 343118 | 733510 | Constrained | Constrained | DUNDEE CITY COUNCIL | RSL |  |  |  | Brownfield | No | No | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200728 | H18 | 2007-04-01 | 0.25972 | PRINCES STREET | 340941 | 730852 | Constrained | Constrained | DUNDEE CITY COUNCIL | Private | PREAPP/001/2019 |  |  | Brownfield | No | No | 20 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200807 | H04 | 2008-04-01 | 0.44319 | QUARRY GARDENS | 337130 | 732089 | Constrained | Planning Consent | DUNDEE CITY COUNCIL | Private |  |  |  | Brownfield | No | No | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201205 | H02 | 2012-04-01 | 0.56489 | EARN CRESCENT, LAND AT | 336292 | 730903 | Constrained | Constrained | DUNDEE CITY COUNCIL | Private |  |  |  | Brownfield | No | No | 20 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201220 | H19 | 2012-04-01 | 0.41142 | BARNS OF CLAVERHOUSE ROAD, MOM PHASE 4 | 340911 | 733631 | Constrained | Planning Consent | DUNDEE CITY COUNCIL | Private |  |  |  | Brownfield | No | No | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201413 | H03 | 2014-04-01 | 3.4021 | CLATTO, LAND AT | 336967 | 734365 | Constrained | Constrained | SCOTTISH WATER | Private |  |  |  | Brownfield | No | No | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 60
201424 | H47 | 2014-04-01 | 1.5713 | STRATHYRE AVENUE, LAND TO EAST OF | 347040 | 732767 | Constrained | Constrained | PRIVATE | Private |  |  |  | Greenfield | No | No | 26 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201509 |  | 2015-04-01 | 1.5242 | LINLATHEN HOUSE, LAND TO EAST OF | 346406 | 732975 | Constrained | Constrained | PRIVATE | Private | 10/00298/FULM |  |  | Greenfield | No | Yes | 60 | 0 | 0 | 0 | 18 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | 281 | 50 | 0 | 0 | 18 | 245 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 60

## Small Sites
4. Small Sites 2023/24
Site_reference | LDP2_reference | Year site added | Site area (ha) | Site address | Easting | Northing | Site type | Site status | Owner / Developer | Tenure type | Planning Application Reference | Last planning approval date | Date completed / expired | Greenfield / Brownfield | Self build | Windfall Site | Site capacity | No of houses | No of flats | Plots complete in survey year 23/24 | Total completions | Units to build
201705B |  | 2010-04-08 | 0.033857 | BROOK STREET, 197, 2/2, BROUGHTY FERRY | 346151 | 730939 | Small Site | Planning Consent | PRIVATE | Private | 10/00066/FULL, 13/00139FULL, 16/00488/FULL, 19/00185/FULL, 22/00283/FULL | 2022-06-02 | 2022-05-10 | Brownfield | No | Yes | 1 | 0 | 1 | 0 | 0 | 1
201705K |  | 2016-12-08 | 0.18299 | DUNDEE ROAD, HOLLY HILL, 69 | 344419 | 731195 | Small Site | Planning Consent | PRIVATE | Private | 16/00832/FULL, 19/00845/FULL, 22/00651/FULL | 2022-11-24 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 0
201805C |  | 2017-05-24 | 0.040016 | GLAMIS ROAD, 28A | 336991 | 730301 | Small Site | Planning Consent | PRIVATE | Private | 17/00266/FULL, 21/00451/FULL | 2021-08-19 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
201805D |  | 2017-06-01 | 0.15268 | HAREFIELD ROAD, 16, LAND TO EAST OF | 338201 | 731821 | Small Site | Planning Consent | PRIVATE | Private | 17/00247/FULL, 22/00010/FULL | 2022-03-10 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
201805M |  | 2018-03-26 | 0.18637 | ARBROATH ROAD, NORTH GRANGE FARM | 348337 | 733354 | Small Site | Planning Consent | PRIVATE | Private | 18/00053/FULL, 21/00123/FULL | 2021-05-07 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
202004P |  | 2020-01-31 | 0.051985 | ROCKFIELD CRESCENT, 7, LAND TO NORTH | 338252 | 730106 | Small Site | Planning Consent | PRIVATE | Private | 19/00914/PPPL, 23/00511/PPPL | 2023-09-29 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
202032A |  | 2020-07-31 | 0.025906 | SYMERS STREET, LAND TO EAST OF 6 | 338543 | 734031 | Small Site | Planning Consent | PRIVATE | Private | 20/00232/FULL, 23/00474/FULL | 2023-09-29 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
202035A |  | 2020-09-04 | 0.049833 | ADELAIDE PLACE, BOWLING GREEN, LAND TO WEST | 339508 | 731114 | Small Site | Planning Consent | PRIVATE | Private | 20/00310/PPPL, 23/00314/FULL | 2023-08-28 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
202035C |  | 2020-10-02 | 0.13039 | ALBANY ROAD, 50, GARDEN GROUND TO SOUTH | 344782 | 731354 | Small Site | Planning Consent | PRIVATE | Private | 20/00289/PPPL, 23/00839/PPPL | 2024-02-02 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
202043 |  | 2020-11-06 | 0.012892 | BROWN STREET, 75/77, BROUGHTY FERRY | 346017 | 730834 | Small Site | Planning Consent | PRIVATE | Private | 20/00529/PPPL, 22/00547/FULL | 2022-11-18 |  | Brownfield | No | Yes | 2 | 0 | 2 | 0 | 0 | 2
202061F |  | 2021-05-12 | 0.13032 | AMERICANMUIR ROAD, 38, GARDEN GROUND | 338540 | 733383 | Small Site | Planning Consent | PRIVATE | Private | 20/00690/FULL | 2021-05-12 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
202105B |  | 2021-07-01 | 0.022691 | SPRINGFIELD, 8, G/0 | 339325 | 729829 | Small Site | Planning Consent | PRIVATE | Private | 20/00618/FULL | 2021-07-16 |  | Brownfield | No | Yes | 2 | 0 | 2 | 0 | 0 | 2
202105C |  | 2021-08-01 | 0.072435 | FREDERICK STREET, 45, GARDEN GROUND | 338778 | 733449 | Small Site | Planning Consent | PRIVATE | Private | 20/00721/FULL, 22/00756/FULL | 2023-02-08 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
202105D |  | 2021-10-01 | 0.021458 | NORTH STREET, 40 | 339958 | 731642 | Small Site | Planning Consent | PRIVATE | Private | 21/00008/FULL | 2021-10-21 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
202105G |  | 2021-08-21 | 0.010331 | REFORM STREET, 51, 2/2, CAFE | 340245 | 730375 | Small Site | Planning Consent | PRIVATE | Private | 21/00501/FULL | 2021-08-27 |  | Brownfield | No | Yes | 1 | 0 | 1 | 0 | 0 | 4
202105I |  | 2021-08-01 | 0.11464 | STRATHERN ROAD, 140 | 345677 | 731472 | Small Site | Planning Consent | PRIVATE | Private | 20/00798/FULL | 2021-08-20 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
202105J |  | 2021-08-01 | 0.056125 | BALGOWAN DRIVE, 7 | 339134 | 733842 | Small Site | Planning Consent | PRIVATE | Private | 21/00471/FULL | 2021-08-17 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
202208 |  | 2022-03-16 | 0.041527 | FORTHILL ROAD, 10 | 346229 | 731308 | Small Site | Planning Consent | PRIVATE | Private | 21/00688/PPPL | 2022-03-16 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
202304 |  | 2022-11-10 | 0.17794 | CAMPHILL ROAD, 65, LAND TO SOUTH | 346894 | 731323 | Small Site | Planning Consent | PRIVATE | Private | 22/00545/FULL | 2022-11-10 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
202305 |  | 2022-11-23 | 0.10384 | BALGILLO ROAD, 157, LAND SOUTH | 346450 | 732090 | Small Site | Planning Consent | PRIVATE | Private | 22/00503/FULL | 2022-11-23 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 0
202306 |  | 2022-11-25 | 0.03012 | LAUDERDALE AVENUE, 88, GARDEN GROUND TO SOUTH | 338288 | 733486 | Small Site | Planning Consent | PRIVATE | Private | 22/00535/PPPL | 2022-11-25 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
202313 |  | 2023-03-31 | 0.28448 | DYKES OF GRAY ROAD, SOUTH OF MAINS OF GRAY FARM | 333577 | 732048 | Small Site | Planning Consent | PRIVATE | Private | 22/00818/FULL | 2023-03-31 |  | Greenfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
202314 |  | 2023-05-18 | 0.033733 | DANIEL TERRACE, 2 | 339440 | 730204 | Small Site | Planning Consent | PRIVATE | Private | 23/00112/FULL | 2023-05-18 |  | Brownfield | No | Yes | 2 | 0 | 2 | 0 | 0 | 2
202315 |  | 2023-05-19 | 0.11554 | BROUGHTY FERRY ROAD, 208 | 342298 | 731118 | Small Site | Planning Consent | PRIVATE | Private | 23/00128/FULL | 2023-05-19 |  | Brownfield | No | Yes | 2 | 2 | 0 | 0 | 0 | 2
202317 |  | 2023-07-28 | 0.0040554 | CLEGHORN STREET, 25A | 338740 | 730664 | Small Site | Planning Consent | PRIVATE | Private | 23/00279/FULL | 2023-07-28 |  | Brownfield | No | Yes | 1 | 0 | 1 | 0 | 0 | 1
202318 |  | 2023-07-31 | 0.0077227 | 86 BELL STREET, UG FLOOR, INDIA BUILDINGS | 340211 | 730614 | Small Site | Planning Consent | PAVILLION PROPERTIES LTD | Private | 23/00345/FULL | 2023-07-31 |  | Brownfield | No | Yes | 1 | 0 | 1 | 0 | 0 | 1
202321 |  | 2023-08-10 | 0.031726 | KINGSWAY, 74, GARDEN GROUND | 340809 | 732504 | Small Site | Planning Consent | PRIVATE | Private | 23/00110/PPPL | 2023-08-10 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
202323 |  | 2023-11-03 | 0.012693 | NETHERGATE, 32 | 340252 | 730132 | Small Site | Planning Consent | PRIVATE | Private | 23/00587/FULL | 2023-11-03 |  | Brownfield | No | Yes | 2 | 0 | 2 | 0 | 0 | 0
202325 |  | 2023-11-23 | 0.014148 | BELL STREET, 86, INDIA BUILDINGS, 2, UPPER GROUND FLOOR | 340216 | 730603 | Small Site | Planning Consent | PAVILLION PROPERTIES LTD | Private | 23/00571/FULL | 2023-11-23 |  | Brownfield | No | Yes | 1 | 0 | 1 | 0 | 0 | 1
202326 |  | 2023-12-21 | 0.017497 | BELL STREET, 86, UNIT 2, INDIA BUILDINGS | 340204 | 730611 | Small Site | Planning Consent | PAVILLION PROPERTIES LTD | Private | 23/00694/FULL | 2023-12-21 |  | Brownfield | No | Yes | 1 | 0 | 1 | 0 | 0 | 0
202327 |  | 2023-12-21 | 0.014137 | BELL STREET, 86, INDIA BUILDINGS, 2, LOWER GROUND FLOOR | 340216 | 730603 | Small Site | Planning Consent | PAVILLION PROPERTIES LTD | Private | 23/00574/FULL | 2023-12-21 |  | Brownfield | No | Yes | 1 | 0 | 1 | 0 | 0 | 0
202402 |  | 2024-01-12 | 0.011603 | BELL STREET, 46 & 50 | 340141 | 730567 | Small Site | Planning Consent | PRIVATE | Private | 23/00701/FULL | 2024-01-12 |  | Brownfield | No | Yes | 1 | 0 | 1 | 0 | 0 | 1
202403 |  | 2024-01-23 | 0.050142 | SHEPHERDS LOAN, LAND SOUTH OF STEPHENS YARD | 338788 | 729671 | Small Site | Planning Consent | PRIVATE | Private | 23/00170/FULL | 2024-01-23 |  | Brownfield | No | Yes | 2 | 2 | 0 | 0 | 0 | 2
202404 |  | 2024-02-05 | 0.31682 | PERTH ROAD, 381, GARDEN GROUND TO EAST | 336752 | 730030 | Small Site | Planning Consent | PRIVATE | Private | 23/00668/FULL | 2024-02-05 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
202405 |  | 2024-02-29 | 0.012526 | BELL STREET, 86, UNIT 1, INDIA BUILDINGS | 340205 | 730599 | Small Site | Planning Consent | PRIVATE | Private | 23/00855/FULL | 2024-02-29 |  | Brownfield | No | Yes | 1 | 0 | 1 | 0 | 0 | 0
202406 |  | 2024-03-15 | 0.035516 | GOTTERSTONE DRIVE, 61 | 344544 | 731906 | Small Site | Planning Consent | PRIVATE | Private | 23/00079/FULL | 2024-03-15 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
202407 |  | 2024-03-20 | 0.13338 | DUNDEE ROAD, 69, WOODCROFT | 344360 | 731160 | Small Site | Planning Consent | PRIVATE | Private | 23/00404/FULL | 2024-03-20 |  | Greenfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 0
201410A |  | 2013-12-13 | 0.13055 | WEST GROVE AVENUE,10 | 337465 | 730045 | Small Site | Under Construction | PRIVATE | Private | 08/00592/FUL, 16/00314/FULL, 19/00376/FULL, 21/00671/FULL | 2022-03-04 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
201410C |  | 2017-01-05 | 0.086026 | BUGHTIES ROAD, 22 | 347058 | 731241 | Small Site | Under Construction | PRIVATE | Private | 16/00889/FULL, 19/00822/FULL | 2020-01-13 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
201510B | H06 | 2023-05-04 | 0.041787 | BURNSIDE STREET, 6-10, SITE OF | 337951 | 731543 | Small Site | Under Construction | PRIVATE | Private | 22/00748/FULL | 2023-05-04 |  | Brownfield | No | No | 2 | 2 | 0 | 0 | 0 | 2
201607L |  | 2015-05-15 | 0.040366 | COLLINGWOOD CRESCENT, 20, LAND TO WEST OF | 347875 | 731329 | Small Site | Under Construction | PRIVATE | Private | 15/00138/FULL, 19/00031/FULL | 2019-05-01 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
201705H |  | 2016-09-14 | 0.057013 | MONIFIETH ROAD, 96 | 347449 | 731179 | Small Site | Under Construction | PRIVATE | Private | 16/00505/FULL | 2016-09-14 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
201805B |  | 2017-05-12 | 0.10675 | MONIFIETH ROAD, 92A | 347338 | 731179 | Small Site | Under Construction | PRIVATE | Private | 16/00745/FULL | 2017-05-12 |  | Brownfield | No | Yes | 2 | 2 | 0 | 0 | 0 | 2
201805G |  | 2017-10-26 | 0.13844 | GIBSON TERRACE, 3, LAND EAST OF | 341179 | 731912 | Small Site | Under Construction | PRIVATE | Private | 17/00594/FULL, 20/00295/FULL | 2020-08-28 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
201805J |  | 2017-11-15 | 0.038506 | PRINCES STREET, 161 | 341072 | 730954 | Small Site | Under Construction | PRIVATE | Private | 17/00769/FULL | 2017-11-15 |  | Brownfield | No | Yes | 3 | 0 | 3 | 0 | 0 | 3
202019D |  | 2020-05-26 | 0.021311 | MONIFIETH ROAD, 69, STONELEE GUEST HOUSE | 346866 | 731047 | Small Site | Under Construction | PRIVATE | Private | 20/00148/FULL | 2020-05-26 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
202031 |  | 2020-07-31 | 0.21123 | PITKERRO MILL | 345088 | 733487 | Small Site | Under Construction | A&G PROPERTIES | Private | 19/00861/FULL | 2020-07-31 |  | Brownfield | No | Yes | 2 | 2 | 0 | 0 | 0 | 2
202035D |  | 2020-11-10 | 0.047011 | SPRINGHILL, 13 | 341571 | 731090 | Small Site | Under Construction | PRIVATE | Private | 20/00459/FULL | 2020-11-10 | 2023-11-10 | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
202035F |  | 2020-11-12 | 0.13097 | DUDHOPE TERRACE, 9 | 339435 | 730892 | Small Site | Under Construction | PRIVATE | Private | 20/00548/FULL | 2020-11-12 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
202035G |  | 2020-11-26 | 0.010618 | VICTORIA ROAD, 10,G1 VICTORIA CHAMBERS | 340214 | 730670 | Small Site | Under Construction | TAYSIDE PROPERTY MANAGEMENT | Private | 20/00133/FULL | 2020-11-26 |  | Brownfield | No | Yes | 1 | 0 | 1 | 0 | 0 | 1
202035H |  | 2020-12-11 | 0.018125 | MURRAYGATE, 39, 1/0 | 340421 | 730459 | Small Site | Under Construction | CASA FRESA HOLDINGS LLP | Private | 20/00509/FULL | 2020-12-11 |  | Brownfield | No | Yes | 3 | 0 | 3 | 0 | 0 | 3
202035K |  | 2021-02-10 | 0.11504 | CAENLOCHAN ROAD, 4 | 345098 | 731659 | Small Site | Under Construction | PRIVATE | Private | 20/00625/FULL | 2021-02-10 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
202061D |  | 2020-08-11 | 0.012799 | NETHERGATE, 138, BASEMENT | 340057 | 729953 | Small Site | Under Construction | PRIVATE | Private | 20/00343/FULL | 2020-08-11 |  | Brownfield | No | Yes | 1 | 0 | 1 | 0 | 0 | 1
202302 |  | 2022-08-23 | 0.10892 | ELLISLEA ROAD, 9, GARDEN GROUND | 345024 | 731414 | Small Site | Under Construction | PRIVATE | Private | 22/00373/FULL | 2022-08-23 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
202311 |  | 2023-03-08 | 0.020025 | LOCHEE ROAD, 142A | 338908 | 730689 | Small Site | Under Construction | PRIVATE | Private | 22/00485/FULL | 2023-03-08 |  | Brownfield | No | Yes | 1 | 0 | 1 | 0 | 0 | 1
202316 |  | 2023-07-21 | 0.085898 | STRATHERN ROAD, 32, GARDEN GROUND | 344271 | 731367 | Small Site | Under Construction | PRIVATE | Private | 23/00199/FULL | 2023-07-21 |  | Brownfield | No | Yes | 1 | 1 | 0 | 0 | 0 | 1
[17 empty] | 69 | 43 | 26 | 0 | 0 | 64

## Removed Sites
5. Removed Sites 2023/24
COMPLETED SITES
Site_reference | LDP2_reference | Year site added | Site area (ha) | Site address | Easting | Northing | Site type | Site status | Owner/Developer | Tenure type | Planning Application Reference | Last planning approval date | Building Warrant Reference | Date completed / expired | Greenfield / Brownfield | Self build | Windfall Site | Site capacity | BW plots withdrawn | No of houses | No of flats | Plots complete in survey year 23/24 | Total completions | Units to build
200719 |  | 1905-06-29 | 0.14 | ESPLANADE, FORMER JACQUES NIGHTCLUB | 347257 | 730953 | Effective | Site Complete | GL RESIDENTIAL | Private | 11/00340/FULL | 2011-09-05 | 12/00395/NBUILD | 2024-02-29 | Brownfield | No | Yes | 11 | 0 | 0 | 11 | 1 | 11 | 0
201506 |  | 1905-07-07 | 0.12 | CLAVERHOUSE OLD ROAD, LAND TO EAST OF 1 | 340818 | 733650 | Effective | Site Complete | RIVERVIEW CONSTRUCTION LTD | Private | 16/00987/FULL | 2017-08-04 | 18/00146/DOM1 | 2023-05-23 | Brownfield | No | Yes | 4 | 0 | 4 | 0 | 4 | 4 | 0
201812 |  | 1905-07-10 | 0.1 | RAGLAN STREET, 5 | 341183 | 731151 | Effective | Site Complete | JF KEGS | RSL | 18/00984/FULL | 2018-12-20 | 22/00206/DOM1 | 2023-12-04 | Brownfield | No | Yes | 16 | 0 | 0 | 16 | 16 | 16 | 0
202215 |  | 2022 | 0.13 | STRATHMARTINE ROAD, 347-349 | 338960 | 733333 | Small | Site Complete | PRIVATE | Private | 22/00444/FULL | 2022-08-29 | 22/00464/dom1 | 2024-03-15 | Brownfield | No | Yes | 1 | 0 | 1 | 0 | 1 | 1 | 0
201009A | H30 | 2018-11-15 | 0.47446 | HADDINGTON AVENUE (Phase 1) | 343571 | 733519 | Effective | Site Complete | MERCHANT/HOME SCOTLAND | Private/RSL | 18/00224/FULL | 2019-09-19 | 18/00744/DOM1 | 2023-05-11 | Brownfield | No | No | 13 | 0 | 13 | 0 | 2 | 13 | 0
201303 |  | 2013-04-01 | 1.2203 | PITKERRO ROAD, 189-197 | 342685 | 732806 | Effective | Site Complete | HOME SCOTLAND | RSL | 16/01057/FULL, 19/00807/FULL | 2021-06-09 | 18/00634/DOM1 | 2024-03-26 | Brownfield | No | Yes | 29 | 0 | 19 | 10 | 29 | 29 | 0
201601 |  | 2015-07-28 | 0.19663 | GARDYNE ROAD, WINNOCKS, 1 | 343984 | 731379 | Effective | Site Complete | PRIVATE | Private | 15/00416/FULL, 17/00947/FULL, 22/0018/NMV, 23/0019/NMV | 2018-02-08 | 17/00711/DOM1 | 2023-04-04 | Brownfield | No | Yes | 7 | 0 | 0 | 7 | 7 | 7 | 0
201702 |  | 2016-07-01 | 0.4596 | GRAY STREET, 44 | 337271 | 731747 | Effective | Site Complete | DEANSCOURT LTD | Private | 16/00362/FULL | 2016-07-01 | 18/00092/DOM1 | 2023-06-01 | Brownfield | No | Yes | 14 | 0 | 14 | 0 | 14 | 14 | 0
201826A | H29 | 2017-10-16 | 2.1476 | SUMMERFIELD GARDENS NORTH | 343648 | 733206 | Effective | Site Complete | INVERTAY HOMES | Private | 17/00307/FULL | 2017-10-16 | 17/00650/DOM1 | 2023-09-29 | Brownfield | No | No | 43 | 3 | 40 | 0 | 3 | 40 | 0
201904A |  | 2018-05-07 | 0.13366 | PERTH ROAD, 474, LAND TO EAST OF COACH HOUSE | 337685 | 729805 | Small Site | Site Complete | PRIVATE | Private | 18/00129/FULL, 21/00086/FULL | 2021-05-07 | 21/00461/DOM2 | 2023-09-01 | Brownfield | No | Yes | 1 | 0 | 1 | 0 | 1 | 1 | 0
201904F |  | 2018-09-06 | 0.021746 | ALBERT SQUARE, 21 | 340324 | 730464 | Small Site | Site Complete | PRIVATE | Private | 18/00454/FULL | 2018-09-06 | 19/00085/DOM1 | 2023-04-12 | Brownfield | No | Yes | 2 | 0 | 0 | 2 | 2 | 2 | 0
201904G |  | 2018-10-15 | 0.08497 | RIVER CRESCENT, GARDEN GROUND WEST OF BURNSIDE | 336537 | 729831 | Small Site | Site Complete | PRIVATE | Private | 18/00595/FULL, 20/00129/FULL | 2020-04-30 | 20/00330/DOM2 | 2023-11-01 | Brownfield | No | Yes | 1 | 0 | 1 | 0 | 1 | 1 | 0
202002 |  | 2019-05-28 | 6.4486 | LIFF HOSPITAL | 334641 | 732800 | Effective | Site Complete | MILLER HOMES | Private | 18/00406/FULL, 18/00407/FULL | 2019-05-28 | 18/00564/DOM1 | 2023-06-06 | Brownfield | No | Yes | 54 | 0 | 54 | 0 | 1 | 54 | 0
202004L |  | 2019-10-25 | 0.21775 | PITKERRO MILL | 345105 | 733477 | Small Site | Site Complete | DEWLOR DEVELOPMENTS | Private | 19/00560/FULL, 23/00238/FULL | 2023-08-02 | 19/00493/DOM1 | 2024-03-25 | Brownfield | No | Yes | 2 | 0 | 2 | 0 | 2 | 2 | 0
202019C |  | 2020-05-20 | 0.027588 | DOUGLAS TERRACE, 12 | 339426 | 730922 | Small Site | Site Complete | PRIVATE | Private | 16/00702/FULL, 20/00143/FULL | 2020-05-20 | 21/00464/DOM2 | 2024-01-30 | Brownfield | No | Yes | 1 | 0 | 1 | 0 | 1 | 1 | 0
202019F |  | 2020-06-25 | 0.11537 | ALBANY ROAD, 39A | 344896 | 731442 | Small Site | Site Complete | PRIVATE | Private | 20/00292/FULL | 2020-06-25 | 20/00400/DOM4 | 2023-08-17 | Brownfield | No | Yes | 2 | 0 | 0 | 2 | 2 | 2 | 0
202032C |  | 2020-09-02 | 0.20667 | FAIRFIELD ROAD, 10 | 344619 | 731407 | Small Site | Site Complete | WEST DEVELOPMENTS (SCOTLAND) LTD | Private | 20/00162/FULL, 21/00702/FULL, 22/00367/FULL | 2022-07-29 | 21/00850/DOM1 | 2023-04-04 | Brownfield | No | Yes | 2 | 0 | 2 | 0 | 1 | 2 | 0
202061G |  | 2021-02-23 | 0.4224 | DYKES OF GRAY, BRAESIDE | 334221 | 732256 | Small Site | Site Complete | PRIVATE | Private | 20/00791/FULL | 2021-02-23 | 21/00576/DOM2 | 2023-08-18 | Brownfield | No | Yes | 1 | 0 | 1 | 0 | 1 | 1 | 0
202061H |  | 2021-04-21 | 0.078396 | NORTH GRANGE FARM, LAND TO EAST OF FARMHOUSE | 348471 | 733313 | Small Site | Site Complete | PRIVATE | Private | 20/00840/FULL | 2021-04-12 | 21/00774/DOM2 | 2023-07-17 | Brownfield | No | Yes | 1 | 0 | 1 | 0 | 1 | 1 | 0
202071 |  | 2021-02-21 | 0.12897 | SOAPWORK LANE, SOAPWORK LANE HOUSE | 340134 | 730639 | Effective | Site Complete | HILLCREST HA | RSL | 20/00714/FULL | 2021-02-24 | 20/00595/DOM1 | 2023-04-12 | Brownfield | No | Yes | 15 | 0 | 0 | 15 | 15 | 15 | 0
202105H |  | 2021-12-01 | 0.34847 | SOUTHAMPTON ROAD, FORMER CRAIGIE HOUSE, LAND AT | 343560 | 731345 | Small Site | Site Complete | DUNDEE CITY COUNCIL | Local Authority | 21/00634/FULL | 2021-12-14 | 21/00663/DOM2 | 2023-08-25 | Brownfield | No | Yes | 1 | 0 | 1 | 0 | 1 | 1 | 0
202105K |  | 2021-08-01 | 0.01514 | SOUTH TAY STREET, 28, GROUND & BASEMENT | 339909 | 730015 | Small Site | Site Complete | RD DEVELOPMENTS LTD | Private | 21/00361/FULL | 2021-08-26 | 21/00711/DOM4 | 2023-05-11 | Brownfield | No | Yes | 2 | 0 | 0 | 2 | 2 | 2 | 0
202207 |  | 2019-01-21 | 0.118 | BUCHANAN STREET, ELECTRIC SUB-STATION | 340869 | 731410 | Effective | Site Complete | PRIVATE | RSL | 18/00779/PPPL, 21/00934/APCONL | 2022-04-21 | 22/00256/DOM1 | 2024-03-01 | Brownfield | No | Yes | 14 | 0 | 0 | 14 | 14 | 14 | 0
[18 empty] | 237 | 3 | 155 | 79 | 122 | 234 | 0
CONSENT EXPIRED
Site_reference | LDP2_reference | Year site added | Site area (ha) | Site address | Easting | Northing | Site type | Site status | Owner/Developer | Tenure type | Planning Application Reference | Last planning approval date | Building Warrant Reference | Date completed / expired | Greenfield / Brownfield | Self build | Windfall Site | Site capacity | BW plots withdrawn | No of houses | No of flats | Plots complete in survey year 23/24 | Total completions | Units to build
202041 |  | 2020-12-14 | 0.083428 | CONSTABLE STREET, LOWER DENS WORKS, BLOCK G | 340826 | 730806 | Effective | Consent Expired | STABLES DEVELOPMENT LLP | Private | 20/00572/FULL | 2020-12-14 |  | 2023-12-14 | Brownfield | No | Yes | 24 | 0 | 0 | 24 | 0 | 0 | 24
202055 |  | 2021-03-22 | 0.035304 | TANNADICE STREET - 28-30, COURT STREET - 32 | 340729 | 731660 | Effective | Consent Expired | ARB PROPERTIES | Private | 19/00925/FULL, 20/00784/FULL | 2021-03-22 |  | 2024-03-22 | Brownfield | No | Yes | 7 | 0 | 0 | 7 | 0 | 0 | 7
201510A | H06 | 2020-01-27 | 0.14348 | HIGH STREET, LOCHEE, SITE OF WEAVERS VILLAGE | 337888 | 731469 | Effective | Consent Expired | HILLCREST HA | RSL | 19/00738/FULL | 2020-01-27 | 21/00029/DOM1 |  | Brownfield | No | No | 14 | 0 | 0 | 14 | 0 | 0 | 14
SMALL SITE - CONSENT EXPIRED
Site_reference | LDP2_reference | Year site added | Site area (ha) | Site address | Easting | Northing | Site type | Site status | Owner/Developer | Tenure type | Planning Application Reference | Last planning approval date | Building Warrant Reference | Date completed / expired | Greenfield / Brownfield | Self build | Windfall Site | Site capacity | BW plots withdrawn | No of houses | No of flats | Plots complete in survey year 23/24 | Total completions | Units to build | Column1 | Column2
201705G |  | 2016-06-24 | 0.14695 | DUDHOPE TERRACE, 7 | 339493 | 730910 | Small Site | Consent Expired | PRIVATE | Private | 16/00277/FULL, 19/00797/FULL | 2019-12-19 | 19/00655/DOM4 | 2022-12-19 | Brownfield | No | Yes | 1 | 0 | 1 | 0 | 0 | 0 | 1
202019E |  | 2020-06-25 | 0.96804 | VICTORIA ROAD, 1, BROUGHTY FERRY | 345373 | 731349 | Small Site | Consent Expired | PRIVATE | Private | 20/00176/FULL | 2020-06-25 |  | 2023-06-25 | Brownfield | No | Yes | 3 | 0 | 0 | 3 | 0 | 0 | 3
202035B |  | 2020-08-31 | 0.0095214 | ERSKINE STREET, 20 | 340962 | 731134 | Small Site | Consent Expired | PRIVATE | Private | 20/00365/FULL | 2020-08-31 |  | 2023-08-31 | Brownfield | No | Yes | 1 | 0 | 1 | 0 | 0 | 0 | 1
202035I |  | 2021-01-06 | 0.012996 | HILLTOWN, 245 | 340051 | 731225 | Small Site | Consent Expired | PRIVATE | Private | 20/00631/FULL | 2021-01-06 |  |  | Brownfield | No | Yes | 1 | 0 | 0 | 1 | 0 | 0 | 1
202035J |  | 2021-01-13 | 0.025383 | COMMERCIAL STREET, 84, 2/1 | 340337 | 730395 | Small Site | Consent Expired | CARDROSS ESTATES | Private | 20/00612/FULL | 2021-01-13 |  | 2024-01-13 | Brownfield | No | Yes | 1 | 0 | 0 | 1 | 0 | 0 | 1
202035L |  | 2021-03-09 | 0.080352 | WEST BELL STREET, 1A | 340006 | 730465 | Small Site | Consent Expired | PRIVATE | Private | 20/00644/FULL | 2021-03-09 |  | 2024-03-09 | Brownfield | No | Yes | 3 | 0 | 0 | 3 | 0 | 0 | 3