SERVICE PLAN 2010 - 2012

CONTENTS

Strategic Statement by Assistant Chief Executive	4

Our Role in fulfilling the Council Plan	4

Key Challenges from the External Environment	5

Key Department Priorities	5

Taking the Department Forward	5

Department Objectives	6

Produce and report on the Community Planning and Corporate Plans to focus on delivering outcomes.	7

Develop and support the governance structure of the Dundee Partnership to deepen partnership working.	8

Manage a programme of reviews and performance assessments to deliver change, improvement and efficiency savings for the Council.	9

Co-ordinate and support the delivery of the "getting it right for every child" integrated children's services strategy	10

Coordinate and support the delivery of projects to ensure people experience fewer social inequalities	11

Coordinate and support the delivery of projects to ensure people experience fewer health inequalities	13

Deliver the National Entitlement Card in Dundee to contribute to people receiving high quality and accessible local services	14

Support elected members to help them deliver their role	15

Support the Chief Executive to deliver best value and customer service excellence	16

Improve the efficiency and effectiveness of the corporate planning department	17

Performance Review	22

CORPORATE PLANNING DEPARTMENT SERVICE PLAN 2010-2012

## Strategic Statement by Assistant Chief Executive

This service plan sets out how the Corporate Planning department will meet the twin aims of the Council Plan to deliver the outcomes for the citizens of Dundee as expressed in the Single Outcome Agreement and to improve services and become a Best Value Council.  The department's overall purpose is to provide advice and guidance to the leadership of the Council to manage change, and the focus of our activity is leadership of the Community Planning and internal planning processes, and ensuring the Council meets the Best Value criteria.

## Our Role in Fulfilling the Council Plan

- Aim One - to deliver the outcomes expressed in the SOA

The Corporate Planning department is responsible for development of the Dundee Partnership and its Single Outcome Agreement and Local Delivery Plan, along with regular monitoring reports on progress towards achieving the outcomes. The Department has overall lead responsibility for the development of the Dundee Partnership and Community planning. Officers from the department have particular responsibilities for policy areas such as community planning, community regeneration, integrated children's services, health improvement and financial inclusion, and will therefore play a lead role in implementing specific actions under the following Council objectives and SOA outcomes listed:

Getting it right for every child

-	our children will be safe, healthy, active, nurtured, achieving, respected, responsible and included

Quality of Life and Social Inclusion

-	our people will experience fewer social inequalities

-	our communities will have high quality and accessible local services and facilities

Healthier Safer communities

-	our people will experience fewer health inequalities

- Aim Two - to improve services and become the Best Value Council

The Corporate Planning department will have a major role in ensuring that the Council improves services and becomes more efficient.  Officers from the department will play a lead role in implementing the following specific actions:

Corporate Improvement

-	Review delivery options for Council Services to achieve cost efficiencies.

-	Develop a shared services programme with other public sector bodies.

-	Create and implement a corporate improvement programme to modernise the council's working methods to achieve efficiencies.

-	develop an annual programme of Public Sector Improvement Framework assessments

- 	continue to develop the lean service programme to deliver efficiencies

Customer Satisfaction

-	maintain the National Entitlement Card system for a range of services

-	ensure there is regular measurement of customer satisfaction

-	publish a customer excellence standard

Monitoring & Evaluation

-	ensure that all departments and service teams have a plan linked to their role in delivering the Single Outcome Agreement and Council Plan

-	publish an annual report on the Single Outcome Agreement and Council Plan and quarterly monitoring reports on priority actions and indicators

-	carry out an annual review of the Council's scrutiny arrangements

## Key Challenges from the External Environment

The key external pressures facing the department are:

- Best Value external inspections of Council governance and performance

- financial pressures to achieve savings affecting all public services which may encourage our partners to narrow their focus to core statutory requirements

- ongoing levels of deprivation and health inequality

- expectation of modern, digital , customer-focused services

## Key Department Priorities

Taking account of the above and the Council Plan priorities, the department's key priorities are:

- Co-ordinating delivery of the SOA, Council Plan and Integrated Children's Service Plan

- Facilitating and developing the Dundee Partnership

- Leading the Corporate Improvement Plan in line with Best Value and helping the council achieve its targeted level of efficiency savings

- Reduction in the levels of deprivation and inequality highlighted in the SOA

## Taking the Department Forward

In order to build the Corporate Planning Department's capacity to improve and to meet the objectives set out in this plan, the department will:

-	carry out a departmental assessment under the Public Sector Improvement Framework and apply the lessons to the development of corporate and community planning.

-	develop whole system approaches to support carrying out lean service reviews of key services

-	ensure that all staff have an annual development and appraisal meeting with their manager

-	deploy to corporate electronic records document management system

- 	Adopt mobile flexible working policies to improve productivity and save office accommodation space.

## Department Objectives

- Produce and report on the Community Planning and Corporate Plans to focus on delivering outcomes.

- Develop and support the governance structure of the Dundee Partnership to deepen partnership working.

- Manage a programme of reviews and performance assessments to deliver change, improvement and efficiency savings for the Council.

- Co-ordinate and support the delivery of the "getting it right for every child" integrated children's services plan

- Coordinate and support the delivery of projects to ensure people experience fewer social inequalities.

- Coordinate and support the delivery of projects to ensure people experience fewer health inequalities

- Deliver the National Entitlement Card in Dundee to contribute to people receiving high quality and accessible local services

- Support elected members to help them deliver their role.

- Support the Chief Executive to deliver best value and customer service excellence

- Improve the efficiency and effectiveness of the corporate planning department

## Objective: Produce and report on the Community Planning and Corporate Plans to focus on delivering outcomes.

| Action Plan | Lead Officer | Completion Date |
| --- | --- | --- |
| Produce a delivery plan and two annual reports for the Single Outcome Agreement on behalf of the Dundee Partnership. | Peter Allan | June 2012 |
| Produce a Council Plan and two Council Plan annual reports. | Paul Carroll | June 2012 |
| Implement the Carbon Reduction Strategy | Chris Ward | June 2012 |
| Produce an annual report on the Council's scrutiny arrangements. | Chris Ward | January 2011 |
| Improve the online plan and performance databases to facilitate the efficient production of quarterly monitoring reports for the Improvement & Efficiency Committee. | Paul Carroll | June 2011 |

| Performance Indicators for this objective | Baseline | Target |
| --- | --- | --- |
| Proportion of top priority performance indicators (Council Plan and a basket of service KPIs approved by the Improvement & Efficiency Committee) showing improvement or maintained performance over declined. | 79% | 80% |
| Carbon Footprint of the City Council (tonnes) (2008/2009) | 51,439 (2008 / 09) | -10% by 2013 |
| Proportion of Council Plan actions behind schedule or at risk of not meeting completion dates. | 6% | <5% |
| Percentage of items in plan monitoring database implemented on schedule. | 93% | >94% |

## Objective: Develop and support the governance structure of the Dundee Partnership to deepen partnership working.

| Action Plan | Lead Officer | Completion Date |
| --- | --- | --- |
| Strengthen Partnership working at a strategic level and address complex operational areas | Peter Allan | March 2012 |
| Review partnership structures to ensure that the respective roles and responsibilities of different groups are clear to minimise overlap | Peter Allan | March 2011 |
| Set partnership aims at an appropriate level, supported by relevant indicators and monitor impact and progress | Peter Allan | March 2011 |
| Establish shared, clearly understood priorities for spending anticipating reduction in resources | Chris Ward /Peter Allan | March 2012 |
| Increase contribution of Elected members to the leadership of the Council and its partnerships | Peter Allan | October 2010 |
| Improve engagement with, and participation of, communities and equalities groups in Dundee Partnership. | Peter Allan/Carole Robertson | March 2012 |

## Objective: Manage a programme of reviews and performance assessments to deliver change, improvement and efficiency savings for the Council.

| Action Plan | Lead Officer | Completion Date |
| --- | --- | --- |
| Review delivery options for Council Services to achieve cost efficiencies. | Chief Executive | March 2012 |
| Develop a shared services programme with other public sector bodies. | Chief Executive | March 2012 |
| Create and implement a corporate improvement programme to modernise the council's working methods to achieve efficiencies. | Chief Executive | March 2012 |
| Deliver a programme of Public Sector Improvement Framework self assessments across the Council. | Tanya Brienesse | March 2012 |

| Performance Indicators for this objective | Baseline | Target |
| --- | --- | --- |
| Annual total efficiency savings. | 1.95% | 2% pa |

## Objective: Co-ordinate and support the delivery of the "getting it right for every child" integrated children's services strategy

| Action Plan | Lead Officer | Completion Date |
| --- | --- | --- |
| Develop and implement the GIRFEC Framework across integrated children's services | Bert Sandeman | March 2012 |
| Chair and support the Strategic Planning and Implementation Groups for Integrated Children's Services | Chris Ward | March 2012 |
| Produce an annual report on the Integrated Children's Service Plan encompassing the Public Sector Improvement Framework Assessment of Integrated Children's Services | Bert Sandeman | March 2012 |
| Develop and implement the corporate parenting strategy including establishing a corporate parent board and develop the role of looked after children champions | Bert Sandeman | Sept 2010 |
| Review and further develop the joint Action Team process and performance. | Bert Sandeman | Sept 2010 |
| Review and further develop the More Choices More Chances processes and performance. | Bert Sandeman | Sept 2010 |

| Performance Indicators for this objective | Baseline | Target |
| --- | --- | --- |
| 16 - 19 year olds not in positive destinations (MCMC population) | 1,119 | 5% reduction |
| Percentage of PIs in the Integrated Children's Services Plan meeting their targets | new | 100% |

## Objective: Coordinate and support the delivery of projects to ensure people experience fewer social inequalities

| Action Plan | Lead Officer | Completion Date |
| --- | --- | --- |
| Develop a strategy to address poverty in the areas of multiple deprivation. | Assistant Chief Executive | March 2012 |
| Produce a poverty profile for Community Regeneration areas. | Peter Allan | Dec 2010 |
| Establish a Partnership information management group to lead on the production of poverty (and other) indicators and report annually. | Peter Allan | September 2010 |
| Develop a formula to measure partnership resource allocation to Community Regeneration Areas and measure annually with 2010/11 as a baseline | Peter Allan | February 2011 |
| Produce revised Financial Inclusion Strategy and action plan for approval by partners | Derek Miller | June 2010 |
| Facilitate local advice agencies achievement of Scottish National Standards accreditation. | Derek Miller | 31st March 2011 |
| Maximise take up of money and fuel poverty advice. | Derek Miller | March 2012 |
| Increase impact and sustainability of Credit Unions. | Derek Miller | March 2012 |
| Develop and promote affordable credit. | Derek Miller | March 2012 |

| Performance Indicators for this objective | Baseline | Target |
| --- | --- | --- |
| Number of data zones in SIMD 15% most deprived. | 55 (SIMD 2009) | 53 |
| Number of SNS accredited advice agencies number % | 2 28.5% | 7 100% |
| Number of people accessing money and fuel poverty advice services | 3,500 | 4,370 |
| Number of credit union members and value of loans. members loan value | 2842 £379k | 3450 £525k |
| Number of households signed to social tariff per annum. | 350 | 500 |
| Number of growth fund 3 loans issued and levels of payments No of loans % with arrears | 260 25% | 750 10% |

## Objective: Coordinate and support the delivery of projects to ensure people experience fewer health inequalities

| Action Plan | Lead Officer | Completion Date |
| --- | --- | --- |
| Facilitate the Council's contribution to the development and implementation of the Tayside Health Equity Strategy | Peter Allan | 2012 |
| Produce and implement Corporate Health Improvement Action Plan incorporating the national review of Equally Well | Carole Robertson | March 2011 |
| Review and re-establish the Corporate Health Network | Carole Robertson | October 2010 |
| Co-ordinate the Council's implementation of Towards a Mentally Flourishing Scotland | Carole Robertson | 2012 |
| Enable Licensing Forum to review policy to secure a focus on public health objectives in Licensing Board decisions | Carole Robertson | December 2010 |

| Performance Indicators for this objective | Baseline | Target |
| --- | --- | --- |
| Local WEMWBS scores/range to reflect changes to mental wellbeing city-wide | Dundee Mean 27.74 | Increase |

## Objective: Deliver the National Entitlement Card in Dundee to contribute to people receiving high quality and accessible local services

| Action Plan | Lead Officer | Completion Date |
| --- | --- | --- |
| In partnership with the transport dept and travel companies develop Commercial Ticketing / Travel applications for the NEC. | Elena Brown | January 2011 |
| Extend the current partnership with University of Abertay Dundee to other Dundee HE / FE Institutions to provide NEC Matriculation / Registration Cards. | Elena Brown | September 2012 |
| Improve the current application process for the Dundee NEC. | Elena Brown | March 2011 |
| Undertake a scoping exercise for the delivery of a Visitor Card. | Elena Brown | January 2011 |
| Issue NEC to council staff in association with a facilities access application for the National Entitlement Card capable of being utilised in Dundee House, Grove and Downfield House. | Elena Brown | October 2011 |

| Performance Indicators for this objective | Baseline | Target |
| --- | --- | --- |
| % of eligible Dundee Citizens that have a National Entitlement Card | 33 (31/12/09) | 50 |
| % of Secondary School Pupils that have a National Entitlement Card. | 95 (31/12/09) | 95 |
| % of National Entitlement Card Customer Satisfied from Customer Satisfaction Survey. | Not yet undertaken | 85 as satisfied or very satisfied. |
| Average transaction time from receipt of card application by Customer Services to card in hand of Customer. | 15 working days | 10 working days |

## Objective: Support elected members to help them deliver their role

| Action Plan | Lead Officer | Completion Date |
| --- | --- | --- |
| Develop, pilot and implement an electronic system to manage Councillors' enquiries from constituents | Bill Findlay | March 2011 |
| Carry out an annual review of Councillors' personal development plans, and continue to deliver training and development opportunities in response to needs identified by members | Bill Findlay | March 2012 |
| Provide a programme of briefings, seminars and training sessions to keep Councillors informed of current policy issues | Bill Findlay | March 2012 |

| Performance Indicators for this objective | Baseline | Target |
| --- | --- | --- |
| % of members delighted or very satisfied with the services provided by the Members Support Unit | 98% (March 2010) | 100% |
| % of members who agree that the training and personal development opportunities offered by the Council help their effectiveness | 96% | 100% |

## Objective: Support the Chief Executive to deliver best value and customer service excellence

| Action Plan | Lead Officer | Completion Date |
| --- | --- | --- |
| Increase the co location of services in the community | Assistant Chief Executive | March 2011 |
| Chair the One Stop Shop Project board to Create one-stop-shop for services in the new Dundee House. | Paul Carroll | October 2011 |
| Chair the Website Steering Group to create a dynamic Council website platform for self services. | Paul Carroll | March 2012 |
| Publish a council customer excellence strategy. | Paul Carroll | September 2010 |

| Performance Indicators for this objective | Baseline | Target |
| --- | --- | --- |
| Overall levels of customer satisfaction (annual survey) - average of last three years. Council image index with telephone contacts with website with office visit | 64% 87% 84% 87% | Increasing trends |
| % o formal complaints responded to in target time (5 days ) | 56% | 95% |
| Volume of online transactions | 73,686 (08/09) | 20% increase |

## Objective: Improve the efficiency and effectiveness of the corporate planning department

| Action Plan | Lead Officer | Completion Date |
| --- | --- | --- |
| Carry out a departmental assessment under the Public Sector Improvement Framework and apply the lessons to the development of corporate and community planning. | Paul Carroll | Dec 2011 |
| Develop whole system approaches to support carrying out lean service reviews of key services. | Jim Duffy | Mar 2012 |
| Ensure that all staff have an annual development and appraisal meeting with their manager | Chris Ward | Mar 2011 |
| Deploy the corporate electronic records document management system. | Bill Findlay | June 2011 |
| Adopt mobile flexible working policies to improve productivity and save office accommodation space. | Paul Carroll | April 2012 |

| Performance Indicators for this objective | Baseline | Target |
| --- | --- | --- |
| Desk : officer ratio | 1:1.2 | 8:10 |
| Printing and stationery costs | £10,000 | £5,000 |

| Risk Register The Register includes an assessment of probability on a scale of 1 to 6: 1 unlikely in the opinion of the assessors it will not happen 2 possible although possible, has not happened so far and is unlikely to happen 3 quite possible has happened to neighbouring Councils and could happen here 4 likely has happened in the past and can be expected to happen sometime again 5 very likely has happened in the last three years and can be expected to happen again/accident waiting to happen 6 almost certain has happened several times a year and can be expected to continue happening The probability assessment is coupled to an assessment of severity, on a scale of 1 to 5. This rates the impact of the risk materialising as: insignificant (1); minor (2); significant (3); major (4); or catastrophic (5). |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Service Objective | Nature of risk (1) | Overall Assessment of Probability and Severity (P * S) (2) | Risk Controls (3) | Business Continuity Implications (4) | Lead Officer for managing the risk (5) |
| Produce and report on the Community Planning and Corporate Plans to focus on delivering outcomes. | Reputation loss if failure to administer the statutory requirement in relation to the local government act 2003 (Best Value & Community Planning). | (3 * 4) 12 | Core function for Corporate Planning chief officers. High level commitment to Best Value Improvement Plan. | None | Performance & Improvement Manager |
| Develop and support the governance structure of the Dundee Partnership to deepen partnership working. | Reputation loss if failure to improve / deepen partnership working in relation to external audit community. | (2*3) 6 | Fitness for purpose reviews carried out on Dundee Partnership theme groups to get improvement plans for each. | None | Community Planning Manager |
| Manage a programme of reviews and performance assessments to deliver change, improvement and efficiency savings for the Council. | Financial loss in following years if failure to balance budget if not assisted by quick delivery of saving benefits from corporate change projects during a period of forecast reduction in government grant. | (3*5) 15 | Two additional change managers being appointed to corporate planning plus transfer of Organisational development staff to focus on high level efficiency reviews. | Absence of change management staff during critical period. Requires team approach across the programme of projects. | Assistant Chief Executive |
| Co-ordinate and support the delivery of the "getting it right for every child" integrated children's services strategy. | The death of a child where the Council has a duty of care. | (5*5) 25 | Multi Agency Chief Officers' Group (COG) leading a major review and related improvement plan on child protection procedures and services Director/senior officer level strategic planning group (SPG) leading the implementation of the Integrated Children's Services Plan | Electronic child protection messaging system and client tracking systems requires highest level of resilience and a pool of staff able to respond to emergency messages. | Chief Executive |
| Coordinate and support the delivery of projects to ensure people experience fewer social inequalities. | Reputation loss for failure to improve policies towards better outcomes for people experiencing multiple deprivations. | (2*3) 6 | High priority given in Council Plan to social inclusion / poverty strategy focussed on areas of multiple deprivation. |  | Assistant Chief Executive |

| Coordinate and support the delivery of projects to ensure people experience fewer health inequalities | Reputation loss for failure to improve policies towards better outcomes for people experiencing health inequalities in areas of multiple deprivation. | (2*3) 6 | High priority given in Council Plan to social inclusion / poverty strategy focussed on areas of multiple deprivation. |  | Community Planning manager |
| --- | --- | --- | --- | --- | --- |
| Deliver the National Entitlement Card in Dundee to contribute to people receiving high quality and accessible local services | Fraudulent use of the card for entitlements. Personal privacy is infringed. | (2*2) 4 (2*4) 8 | The card is manufactured to the highest industry standard which protects against copying electronic data plus provides a hot list function plus photo id to prevent use by non card holder. National standards and policies govern the separation of card, card use and card technical data. Data protection is given the highest priority in card management procedures. | Card Management system communication with remote services requires highest level of resilience and pool of customer service staff able to operate it. | Performance & Improvement Manager |

| Support elected members to help them deliver their role. | Reputation loss if decision making or scrutiny process is ineffective. | (3*4) 12 | High contact with chief officers and opportunity to discuss reports with experts. Seminars, briefings, training given plus high quality secretarial support to facilitate answering constituent enquiries. |  | Assistant Chief Executive |
| --- | --- | --- | --- | --- | --- |
| Support the Chief Executive to deliver best value and customer service excellence. | Reputation loss if the quality of customer services is not on a par with highest standards. | (2* 2) 4 | Customer Excellence standard being developed to take forward current customer first strategy. | Corporate Contact Centre approach building up a pool of staff able to cover peaks and emergency absences. Customer Service Systems on highest levels of resilience. | Performance & Improvement Manager |

# Corporate Planning Department

## Performance Review

Overall the department has made the following performance improvements in its priority indicators:

- A rise in the use of Joint Action Teams in integrated children's services from 10 in 2007 to 20 in the current year to date. This indicates and increasing take up by multi agencies of the integrated approach to supporting children in need.

- A maximum 100% satisfaction from Elected Members in the members support service

- An above the Scottish average roll out of the National Entitlement Card was achieved which included replacing all the prior Dundee Discovery Cards with the national card scheme and reaching 95% of all secondary school age children in Dundee

The following indicators have show a declining trend and will be subject to a detailed review in the period ahead:

- A reduction in the amount of affordable credit issued was measured as part of the financial inclusion strategy. This will be a priority issue in the next year. Efforts to boost the take up of credit union membership will aim to reverse this decline.

- The Dundee National Entitlement Card failed to collect measurable customer satisfaction feedback in the last year and this will collected as a priority in the next twelve months and used to identify improvements in the process of applying for or renewing a card.

The full analysis of the department's Key Performance Indicators is contained in the table below. Where relevant these indicators are continued in the current service plan to provide ongoing trends as a baseline for judging the performance of the department in the future.

| Definition | 05/06 | 06/07 | 07/08 | 08/09 | Latest Upd. | Target | Scottish Average | Status (LT) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of young people (16-19 year olds) not in education, training or employment | 11.9 | 11.3 | 11.6 | 11.6 | 31/03/2009 - 11.6 | 11.3 | 9.6 | Maintained |
| Number of Joint Action Teams in operation |  | 10 | 20 | 20 | 31/03/2010 - 20 | 20 |  | Improving |
| Proportion of children and young people (0-18) covered by the client tracking system |  |  | 93 | 93 | 30/09/2009 - 93 | 100 |  | Maintained- target not achieved |
| % of customers satisfied when contacting the Council by web | 87 | 93 | 85 | 83 | 31/10/2009 - 85 | 85 |  | Maintained |
| % of customers satisfied when contacting the Council by phone | 86 | 89 | 87 | 90 | 31/10/2009 - 85 | 87 |  | Maintained |
| % of customers satisfied when contacting the Council in person | 92 | 89 | 89 | 82 | 31/10/2009 - 91 | 89 |  | Maintained |
| Overall profile of the Council over ten criteria in the annual consumer survey (% agreeing with positive statements) | 58 | 66 | 62 | 70 | 31/10/2009 - 62 | 62 |  | Maintained |
| Proportion of performance indicators in the Council's monitoring database that show improvement |  |  | 31.55 | 33.6 | 31/12/2009 - 34.28 | 33.00 |  | Maintained |
| Proportion of projects in the Council's monitoring database that are not behind schedule, abandoned or unlikely to be achieved (%) |  |  | 92.12 | 93.31 | 31/12/2009 - 93.27 | 92.4 |  | Maintained |
| Proportion of Community Planning projects in the Council's monitoring database that are not behind schedule or unlikely to be achieved (%) |  |  | 93.33 | 93.94 | 31/12/2009 - 93.32 | 92.3 |  | Maintained |
| % of members delighted or very satisfied in annual satisfaction survey of all elected members | 91 | 96 | 99 | 100 | 31/03/2009 - 98 | 100 |  | Improving / long term trend |
| % of people in regeneration areas who use expensive forms of credit and retail/store card |  | 45 | 45 | 45 | 31/03/2009 - 45 | 45 |  | Maintained |
| Number of affordable credit providers |  | 2 | 2 | 1 | 31/03/2009 - 1 | 2 |  | Deteriorating |
| Number of loans provided by affordable credit providers |  |  | 332 | 167 | 31/03/2009 - 167 | 209 |  | Deteriorating |
| Value of loans provided by affordable credit providers (£) |  |  | £68,384 | £36,559 | 31/03/2009 - 36,559 | £45,024 |  | Deteriorating |
| Number of advice and information agencies achieving Scottish National Standards |  |  | 0 | 0 | 31/03/2009 - 0 | 7 |  | Target not achieved |
| % of Dundee citizens that have a National Entitlement Card |  |  | 29 | 33 | 31/12/2009 - 33 | 25 | 31.64 | Improving |
| % of Dundee school pupils that have a National Entitlement Card |  |  | 62 | 81 | 31/12/2009 - 95 | 95 |  | Improving |
| % of entitlement card customers satisfied from Customer Satisfaction Survey |  |  | 0 | 0 | 31/03/2010 - survey not complete | 75 |  | Target not achieved |
| Number of local applications on the Dundee Card replicated nationally |  | 4 | 4 | 4 | 31/03/2009 - 4 | 8 |  | Maintained - target not achieved |