REPORT TO:	Policy and Resources Committee - 23 August 2010

REPORT ON:	Information Technology Division Service Plan 2010-2012

REPORT BY:	Head of Information Technology

REPORT NO:	428-2010

1.0	PURPOSE OF REPORT

  - To seek committee approval of the Information Technology Division Service Plan 2010-2012.

2.0	RECOMMENDATIONS

2.1	The Committee is recommended to approve the Information Technology Division Service Plan 2010-2012.

3.0	FINANCIAL IMPLICATIONS

  - The projects and actions identified in the plan will be met from existing revenue and capital budgets.

- MAIN TEXT

4.1	The Information Technology Division’s role is to advise Council and to design, deliver, support and maintain Information Technology (IT) services across the Council. The Division has a key role in providing technology enablers to assist the Council to modernise its service delivery and increase the efficiency and effectiveness of service delivery across all of its areas of responsibilities.

4.2	The proposed Information Technology Division Service Plan 2010-2012 has been developed taking account of the strategic challenges facing the Division along with the priorities set out in the Council Plan 2010-2012. The plan establishes the following key objectives and identifies strategies and projects to ensure they are realised:

- Increase efficiency of corporate and inter-agency processes by deploying software solutions

- Increase Customer satisfaction when in contact with Customer Services

- Extend the provision of Mobile, Flexible and Home working technologies

- Successfully deliver all Information and Technology aspects of the forthcoming major accommodation changes

- Provide an Information and Communications infrastructure which  meets the needs of the organisation and supports service improvement

- Improve the efficiency and effectiveness of the Information Technology Division

  - Further detail on how these objectives will be delivered is identified in the plan. Measurement of performance and targets will allow progress towards meeting these objectives to be monitored. These are also identified within the plan.

5.0	POLICY IMPLICATIONS

5.1 	This Report has been screened for any policy implications in respect of Sustainability, Strategic Assessment, Anti-Poverty, Equality Impact Assessment and Risk Assessment. There are no major issues. The Equality Impact Assessment will be made available on the Council website: http://www.dundeecity.gov.uk/equanddiv/equimpact/ .

- CONSULTATIONS

6.1	The Chief Executive, Depute Chief Executive (Support Services) Director of Finance and Assistant Chief Executive have been consulted.

7.0	BACKGROUND PAPERS

  - Council Plan 2010-2012

  - IT Service Plan EQIA

Mr. Ged Bell.  Head of Information Technology             			Date:  3 August 2010

# INFORMATION TECHNOLOGY DIVISION SERVICE PLAN 2010-2012

## Strategic Statement by Head of Information Technology

This service plan sets out how the Information Technology Division will meet the aims of the Council Plan to deliver the outcomes for the citizens of Dundee as expressed in the Single Outcome Agreement and to improve services and become a Best Value Council.

The Division’s role is to advise Council and to design, deliver, support and maintain Information Technology (IT) services across the Council. The Division has a key role in providing technology enablers to assist the Council to modernise its service delivery and increase the efficiency and effectiveness of service delivery across all of its areas of responsibilities.

The Division’s historic responsibilities were mainly inward looking as an internal provider of services to Council Departments to enable them to fulfil their service provision duties. Over the past four years the Division has transformed its function, developed capability and prioritised direct services to our Citizens by the growth of our on-line services.

## Our Role in Fulfilling the Council Plan

The Council Plan sets out key priorities for the Council as a whole. Through provision of the underpinning information and technology systems, the IT Division has an indirect role in supporting all of the Council's key aims. However, the Council Plan priorities which are most directly relevant to the IT Division are:

- Corporate Change and Improvement Program. The IT Division has a key role in  the following areas within the program:

  - Extend the provision of Mobile, Flexible and Home working technologies

  - Successfully delivering all information and technology aspects of the forthcoming major accommodation changes

  - Provide an Information and Communications infrastructure which  meets the needs of the organisation and supports service improvement

- Customer Satisfaction. The IT Division has a key role in the following areas:

  - Maximise the use of self-service on-line services for information and transactions

  - Maximise the use of Citizen Account and National Entitlement card to minimise the need for Customers to complete forms when the Council already holds information

  - Increase efficiency of corporate processes by deploying software solutions

## Key Challenges from the External Environment

The key external pressures facing the Division are:

- Expectation of modern 24x7, on-line , customer-focused services

- financial pressures to achieve savings, with the potential to affect investment in core Information Technology services

- growing requirement to work with other public sector partners and share information

- increasing and ever-changing Information Security threats and the need to maintain public confidence in how the public sector handles customer data.

## Key Divisional Priorities

Taking account of the above and the Council Plan priorities, the division’s key priorities are:

- Make all orders, requests and financial transaction services available via the website

- maximise the use of Citizen Account and National Entitlement Card so that customers don’t need to complete forms when the Council already holds the information

- manage and deliver the Information Technology elements of the major accommodation changes and data-centre relocation which the Council will undertake over the next 12 months

- provide a robust IT infrastructure which supports the changing needs of the Council. These include:

  - Mobile, Flexible and Home Working technology and infrastructure

  - Electronic Document Management technology and infrastructure

  - Centralised, standardised core infrastructure which minimises the lifecycle costs

## Taking the Division Forward

In order to build the Information Technology Division’s capacity to improve and to meet the objectives set out in this plan, the department will:

-	carry out a departmental assessment under the Public Sector Improvement Framework and apply the lessons to the development of Information Technology Services.

-	develop whole system approaches to support carrying out lean service reviews of key services

- 	deploy technologies which increase efficiency of IT services and reduce lifecycle costs

-	ensure that all staff have an annual development and appraisal meeting with their manager and that ensure that individual priorities are closely linked to corporate/divisional priorities

-	deploy corporate electronic records document management system

- 	Adopt mobile flexible working policies to improve productivity and save office accommodation space.

## Division Objectives

- Increase efficiency of corporate and inter-agency processes by deploying software solutions

- Increase Customer satisfaction when in contact with Customer Services

- Extend the provision of Mobile, Flexible and Home working technologies

- Successfully deliver all Information and Technology aspects of the forthcoming major accommodation changes

- Provide an Information and Communications infrastructure which  meets the needs of the organisation and supports service improvement

- Improve the efficiency and effectiveness of the Information Technology Division

## Objective: Increase efficiency of corporate and inter-agency processes by deploying software solutions

| Action Plan | Lead Officer | Completion Date |
| --- | --- | --- |
| Development of processes (Workflows, e-forms & reports) and bespoke integrations to support CeRDMS project | Jim Walker | June 2012 |
| Develop & deploy all software solutions to meet Housing Regulator Action Plan recommendations | Norrie McIver | June 2012 |
| Deploy single shared assessment and child protection messaging inter-agency software solution | Jim Walker | Nov 2010 |
| Deploy joined-up systems for inter-departmental/inter-agency service delivery | Jane Crawford | June 2012 |
| Deploy corporate self-service applications to increase efficiency of operation | Jane Crawford | June 2012 |

| Performance Indicators for this objective | Baseline | Target |
| --- | --- | --- |
| Number of CeERDMS processes and integrations deployed | 0 | Increase by 10 p.a. |
| Number of joined-up systems for inter-departmental/inter-agency service delivery (2008/2009) | 15 | Increase by 3 p.a. |
| Number of corporate self-service applications deployed | 3 | Increase by 3 p.a. |

## Objective: Increase Customer satisfaction when in contact with Council Services

| Action Plan | Lead Officer | Completion Date |
| --- | --- | --- |
| Complete the program of delivering online all possible services, requests and payments | John Lawson | June 2012 |
| Deployment of Information Strategy Action Plans - maximising the use of common information & maximising re-use of Citizen and Property Information | Jane Crawford | June 2012 |
| Deployment of applications providing information using Website GIS (Geographical Information System) portal | Paul McGovern | June 2012 |
| Make services more efficient by exploiting a web-based GIS toolkit | Paul McGovern | June 2012 |

| Performance Indicators for this objective | Baseline | Target |
| --- | --- | --- |
| Savings derived from process efficiencies deployed (Information Strategy) | £736K p.a. | Increase by 200K p.a. |
| Number of orders, requests and financial transactions available on the website | 64 | Increase by 8 p.a. |
| Number of services delivered by Contact Centres, CRM systems and Information Strategy | 31 | Increase by 5 p.a. |
| Number of applications providing information using website GIS | 2 | Increase by 3 p.a. |
| Number of services made more efficient by exploiting a web-based GIS toolkit | N/A | Increase by 3 p.a. |

## Objective: Extend the provision of Mobile, Flexible and Home working technologies.

| Action Plan | Lead Officer | Completion Date |
| --- | --- | --- |
| Develop an investment proposal for upgrading the Council's telephony estate to provide telephony for flexible workforce | Ged Bell | Oct 2010 |
| Develop a common software platform for deploying existing Council Software on Mobile devices - to operate in a robust manner over Mobile Phone networks | Ged Bell | Dec 2010 |
| Update IT acceptable use policies to cover home, mobile and flexible working | Ged Bell | Dec 2010 |

| Performance Indicators for this objective | Baseline | Target |
| --- | --- | --- |
| Number of staff who have access to mobile, flexible or home IT Services | 1050 | Increase by 300 p.a. |

## Objective: Deliver all Information and Technology aspects of the forthcoming major accommodation changes

| Action Plan | Lead Officer | Completion Date |
| --- | --- | --- |
| Deliver all aspects of Data Centre provision at Dundee House | Steve Boyd | Jul 2011 |
| Deliver all aspects of Information Technology requirements for staff and visitor use at Dundee House | Steve Boyd | May 2011 |
| Design and deliver resilient Network for Dundee House and interconnect to Shore Tce. Data-centre | Graeme Quinn | Mar 2011 |
| Deploy IP Telephony and increase telephony resilience at Dundee House | Graeme Quinn | Mar 2011 |
| Upgrade central server provision and further consolidate applications onto Citrix VDI platform | Steve Boyd | Apr 2012 |
| Consolidate and upgrade Firewalls prior to Dundee House move | Jim Gorman | Oct 2010 |
| Perform all Major LINUX operating System upgrades prior to Dundee House Move | Jim Gorman | Nov 2010 |
| Upgrade Internet filtering software prior to Dundee House Move | Jim Gorman | Dec 2010 |
| Provision of CeRDMS platform, storage, live environment and e-mail integrations required for Dundee House | Jim Walker | Apr 2011 |
| De-commission all possible stand-alone server based applications prior to Dundee House Move | Jim Walker | Dec 2010 |
| Deploy additional centralised data storage and upgrade central Linux Servers - to increase capacity and resilience prior to Dundee House Move | Tim Simpson | Nov 2010 |
| Update all Systems-based addresses prior to Dundee House move | John Lawson | Apr 2011 |
| Eliminate all possible central print functions and replace with web-based reports or CeRDMS - prior to Dundee House move | Jane Crawford | Apr 2011 |

## Objective: Provide an Information and Communications infrastructure which  meets the needs of the organisation and supports service improvement

| Action Plan | Lead Officer | Completion Date |
| --- | --- | --- |
| Provide access to additional cloud based personal data storage for all schools pupils | Niall Gibb | Apr 2011 |
| Develop patch management and upgrade management policy | Neil Cathro | Feb 2011 |
| Implement upgraded security endpoint protection and laptop encryption | Neil Cathro | April 2011 |
| Consolidate IT asset management information from service desk and software inventory | Neil Cathro | Mar 2011 |

| Performance Indicators for this objective | Baseline | Target |
| --- | --- | --- |
| Annual average cost per IT workstation | £132.35 | Reduce by 2% p.a. |
| Average fix-time for all IT support calls | 12.38 hours | Maintain |
| Uptime of citizen-based internet services | 99.5% | Increase |

## Objective: Improve the efficiency and effectiveness of the Information Technology Division

| Action Plan | Lead Officer | Completion Date |
| --- | --- | --- |
| Carry out a departmental assessment under the Public Sector Improvement Framework and apply the lessons to the development of the delivery of IT services | Jane Crawford | Mar 2012 |
| Ensure that all staff have an annual development and appraisal meeting with their manager | Ged Bell | Dec 2010 |
| Deploy corporate electronic records document management system across IT Division | Ged Bell | April 2011 |
| Adopt mobile flexible working policies to improve productivity and save office accommodation space. | Ged Bell | Oct 2011 |

| Performance Indicators for this objective | Baseline | Target |
| --- | --- | --- |
| Desk : officer ratio | 1:1 | 8:10 |

| Risk Register |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Service Objective | Nature of risk (1) | Overall Assessment of Probability and Severity (P * S) (2) | Risk Controls (3) | Business Continuity Implications (4) | Lead Officer for managing the risk (5) |
| Increase efficiency of corporate and inter-agency processes by deploying software solutions | Loss of key staff | (2 x 4) 8 | Career grade retention program | N | Jane Crawford |
|  | Lack of client department support or resource | (3 x 5) 15 | Well defined user requirements. Client dept. commitment | N | Jane Crawford |
|  | Lack of IT Infrastructure provision | (2 x 4) 8 | Business Continuity Strategy | Y | Tim Simpson |
| Increase Customer satisfaction when in contact with Customer Services | Loss of key staff | (2 x 4) 8 | Career grade retention program | N | Jane Crawford |
|  | Lack of client department support or resource | (3 x 5) 15 | Well defined user requirements. Client dept. commitment | N | Jane Crawford |
|  | Lack of IT Infrastructure provision | (2 x 4) 8 | Business Continuity Strategy | Y | Tim Simpson |
| Extend the provision of Mobile, Flexible and Home working Technologies. | Loss of key staff | (2 x 4) 8 | Career grade retention program | N | Ged Bell |
|  | Lack of client department support or resource | (3 x 5) 15 | Well defined user requirements. Client dept. commitment | N | Ged Bell |
|  | Lack of IT Infrastructure provision | (2 x 4) 8 | Business Continuity Strategy | Y | Tim Simpson |
| Successfully deliver all Information and Technology aspects of the forthcoming major accommodation changes | Loss of key staff | (2 x 4) 8 | Career grade retention program | N | Steve Boyd |
|  | Lack of client department support or resource | (3 x 5) 15 | Well defined user requirements. Client dept. commitment | N | Steve Boyd |
|  | Lack of IT Infrastructure provision | (2 x 4) 8 | Business Continuity Strategy | Y | Tim Simpson |
| Provide an Information and Communications infrastructure which meets the needs of the organisation and supports service improvement | Loss of key staff | (2 x 4) 8 | Career grade retention program | N | Steve Boyd |
|  | Lack of client department support or resource | (3 x 5) 15 | Well defined user requirements. Client dept. commitment | N | Steve Boyd |
|  | Lack of IT Infrastructure provision | (2 x 4) 8 | Business Continuity Strategy | Y | Tim Simpson |

# Information Technology Division - Performance Review

A review of the 2007-2011 IT Division Service Plan had identified that the Division performed well against targets. A reduction in the cost of IT Contracts has allowed financial resources to be invested in improvement areas. Another key area is the continued growth of applications and services being available online and at the Contact Centres. These initiatives are accruing significant Departmental savings. Deployment of low-power thin client desktops and flat screens exceeds targets and both these initiatives reduce cost and carbon footprint. IT support performance and reliability levels continue to improve.

|  | Performance Statistics |  | Improvement Status |  | Benchmarks |  | Commentary |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Definition | Previous Figures (b) = baseline | Latest Figures (b) = baseline | Yearly Trend | Long Term Trend | Average | Best | Latest Update (followed by remedial action if declining performance indicated) |
| % of faults resolved within SLA times (true faults) | 12/09 - 91.85 09/09 - 90.46 06/09 - 90.22 03/09 - 95 | 03/10 - 92.67 |  |  |  |  |  |
| CRT screen replacement with low-powered LCD panel. | 03/09 - 1,392 03/08 - 950 03/07 - 950 | 03/10 - 2,000 |  |  |  |  | All CRT screens throughout the Council have now been replaced with low power LCD equivalents |
| Citizen Account/Corporate Address Gazetteer - increase in number of systems integrated. | 03/09 - 21 03/08 - 18 03/07 - 16 03/06 - 11 | 03/10 - 27 |  |  |  |  | Systems integrated in 2009/10 were Social Work, Emergency system, FPNs, DUNCAN, ASB, Housing |
| Cost of IT Contracts as % of IT budget. | 03/07 - 33 01/06 - 33 03/05 - 33 | 03/09 - 32 |  |  |  |  | Elimination of Teamware mail platform resulting in net saving of £66K per annum. Replacement of DS library system with Civica Spydus resulting in net saving of £25K per annum. Addition of ePlanning services and other software resulting in net increase of £30K per annum. Overall net reduction of £61K per annum (1%) as a result of these initiatives |
| Cost per workstation across the Council (£) | 03/09 - 134 03/08 - 137 | 03/10 - 132.35 |  |  |  |  |  |
| Data cleansing/matching - number of records matched to Citizen Account. | 03/09 - 210,461 03/08 - 135,000 03/07 - 79,000 03/06 - 51,000 | 03/10 - 277,304 |  |  |  |  |  |
| Growth in number of joined-up systems for inter-departmental/inter-agency working. | 03/09 - 9 03/08 - 6 03/07 - 3 | 03/10 - 15 |  |  |  |  | Live this year were JATs,household enquiry for Police/ASB,Active4Life,DUNCAN,Welfare Rights portal, Lettings Contact Centre |
| Growth in online service transactions. | 03/09 - 59 03/08 - 53 03/07 - 47 | 03/10 - 64 |  |  |  |  | Live in 2009/10 were litter FPNs, fly-tipping FPNs, noise FPNs, smoking FPNs and report grafitti |
| Integration of GIS with services provided by Council's CRM/Contact Centres. | 03/09 - 1 03/08 - 1 03/07 - 1 | 03/10 - 3 |  |  |  |  | Pest Control, House Letting, Land Ownership |
| Number of applications providing information via internet GIS portal. | 03/09 - 2 03/08 - 0 03/07 - 0 | 03/10 - 8 |  |  |  |  | Simple location mapping, Elections web site, Winter Maintenance, My Dundee, Ward Mapping, Available Now housing, Housing Letting Areas, Recycling Points all live |
| Number of low-power desktop devices | 03/09 - 1,841 03/07 - 1,771 03/06 - 482 03/05 - 380 | 03/10 - 1,963 |  |  |  |  | Corporate IT policy is to deploy low power NC desktop in preference to PC workstation. More NCs will be deployed during annual bid process for 2010/11 |
| One Stop Shop - growth in number of services provided by Council's CRM/Contact Centres. | 03/09 - 17 03/08 - 15 03/07 - 10 03/06 - 6 | 03/10 - 31 |  |  |  |  | Live in 2009/10 were Rent Account enq at Customer Services, report ASB at Customer Services, report repairs at Customer Services, council emergency system, report road defect, report street lighting, report other P&T fault, pay smoking fine, pay litter fine, pay dog fouling fine, pay parking fine, pay fly tipping fine, pay noise fine, Lettings contact Centre |
| Process efficiencies achieved through the information strategy (£). | 03/09 - 474,000 03/08 - 135,000 03/07 - 100,000 | 03/10 - 736,700 |  |  |  |  | Current efficiencies achieved through the strategy are £736,700 per annum |
| Update of multi-user system access. | 09/09 - 0 12/08 - 0 03/08 - 0 12/07 - 0 | 03/10 - 100 |  |  |  |  | The introduction of 1st line support has reduced the downtime of systems |
| Uptime of Citizen internet services | 12/09 - 99.5 09/09 - 99.5 06/09 - 98.6 03/09 - 99.5 | 03/10 - 99.7 |  |  |  |  | Box Office 99.88%, Formschecker 99.36%, HomePage 99.60%, City Payments 99.93% |