## Table 1 - AHSP Years 1-5
MORE HOMES DIVISION
STRATEGIC HOUSING INVESTMENT PLAN 2018/19-2022/23
Table 1 - AFFORDABLE HOUSING SUPPLY PROGRAMME - Years 1-5 2018/19-2022/23
LOCAL AUTHORITY:Dundee City Council
PROJECT | SUB-AREA | PRIORITY | GEOGRAPHIC COORDINATES (X:EASTING Y:NORTHING) | GEOGRAPHIC CODE (Numeric Value - from Drop Down Table Below) | DEVELOPER | UNITS - TENURE | [6 empty] | UNITS - BUILT FORM |  |  |  | UNITS - TYPE |  |  |  | GREENER STANDARDS | APPROVAL DATE | UNITS SITE STARTS | [5 empty] | UNITS - COMPLETIONS | [5 empty] | SG AHSP FUNDING REQUIREMENT (£0.000M)
|  | Low / Medium / High |  |  |  | Social Rent | Mid Market Rent | LCHO - Shared Equity | LCHO - Shared Ownership | LCHO - Improvement for Sale | PSR | Total Units | Rehab | Off the Shelf | NB | Total Units | GN | Specialist Provision | Type of Specialist Particular Need (If Known) | Total Units by Type | Enter Y or N | Financial Year (Estimated or Actual) | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23 | TOTAL SITE STARTS OVER PERIOD OF SHIP | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23 | TOTAL COMPLETIONS OVER PERIOD OF SHIP | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23 | TOTAL AHSP FUNDING REQUIRED OVER SHIP PERIOD
Charleston Primary School (H65) | Lochee | High | X:335997 Y:731625 | 5 | Abertay Housing Association | 40 | [5 empty] | 40 |  |  | 40 | 40 | 36 | 4 | Wheelchair | 40 | Y | 2017 | 40 |  |  |  |  | 40 |  | 40 |  |  |  | 40 | 2.28 |  |  |  |  | 2.28
Tranent Grove (H34) | North East | High | X:343258 Y:733557 | 6 | Angus Housing Association | 46 | 20 |  |  | 30 |  | 96 |  |  | 96 | 96 | 42 | 4 | N/K | 46 | N | 2018 | 48 | 48 |  |  |  | 96 |  | 48 | 48 |  |  | 96 | 2.06 | 2.06 |  |  |  | 4.12
Brownhill Place | Lochee | High | X:336552 Y:732125 | 5 | Blackwood Housing Association | 25 | [5 empty] | 25 |  |  | 25 | 25 |  | 25 | Wheelchair | 25 | Y | 2018 | 25 |  |  |  |  | 25 |  | 25 |  |  |  | 25 | 1.8 |  |  |  |  | 1.8
Morgan Street | Maryfield | Medium | X:341340 Y:731581 | 5 | Caledonia Housing Association | 28 | [5 empty] | 28 |  |  | 28 | 28 | 22 | 6 | 2 Wheelchair 4 Community Care | 28 | Y | 2017 | 28 |  |  |  |  | 28 | 28 |  |  |  |  | 28 | 1.227 |  |  |  |  | 1.227
Coldside Road | Coldside | Medium | X339451 Y:731944 | 5 | Caledonia Housing Association | 30 | [5 empty] | 30 |  |  | 30 | 30 | 22 | 8 | 2 Wheelchair 6 Supported Accommodation | 30 | Y | 2017 | 30 |  |  |  |  | 30 | 30 |  |  |  |  | 30 | 1.61 |  |  |  |  | 1.61
Derby Street (H40) | Hilltown | High | X:339860 Y:731548 | 9 | Dundee City Council | 83 | [5 empty] | 83 |  |  | 83 | 83 | 51 | 32 | 14 Wheelchair 10 Supported Accommodation | 83 | Y | 2017 | 83 |  |  |  |  | 83 |  | 83 |  |  |  | 83 | 3.112 |  |  |  |  | 3.112
Derby Street (H40) | Hilltown | High | X:339860 Y:731548 | 5 | Hillcrest Housing Association | 58 | 22 |  |  |  |  | 80 |  |  | 80 | 80 | 58 |  |  | 58 | Y | 2017 | 80 |  |  |  |  | 80 |  |  | 80 |  |  | 80 | 5.973 | 0.587 |  |  |  | 6.56
Seagate | Maryfield | Medium | X:340547 Y:730523 | 5 | Hillcrest Housing Association | 28 | [5 empty] | 28 |  |  | 28 | 28 | 28 |  |  | 28 | Y | 2017 | 28 |  |  |  |  | 28 | 28 |  |  |  |  | 28 | 1.711 |  |  |  |  | 1.711
Benvie Road | West End | Medium | X:338883 Y:730599 | 5 | Hillcrest Housing Association | 12 | [5 empty] | 12 |  |  | 12 | 12 |  | 12 | Supported Accommodation | 12 | Y | 2017 | 12 |  |  |  |  | 12 | 12 |  |  |  |  | 12 | 0.432 |  |  |  |  | 0.432
Ellengowan Drive | Maryfield | Medium | X:341766 Y:731145 | 5 | Hillcrest Housing Association | 62 | 71 |  |  |  |  | 133 |  |  | 133 | 133 | 62 | tbc |  | 62 | Y | 2017 | 32 |  | 41 | 52 | 8 | 133 |  |  | 32 | 41 |  | 73 | 2.31 |  | 2.311 | 3.506 | 0.401 | 8.528
St. Mary's Infant School | Lochee | High | X:338016 Y:731339 | 5 | Hillcrest Housing Association | 24 | [5 empty] | 24 |  |  | 24 | 24 | 24 |  |  | 24 | Y | 2017 | 24 |  |  |  |  | 24 | 24 |  |  |  |  | 24 | 1.728 |  |  |  |  | 1.728
Law Nursery | Lochee | High | X:228729 Y:731183 | 5 | Hillcrest Housing Association | 27 | [5 empty] | 27 |  |  | 27 | 27 | 23 | 4 | Wheelchair | 27 | Y | 2018 | 27 |  |  |  |  | 27 |  | 27 |  |  |  | 27 | 1.944 |  |  |  |  | 1.944
Pitkerro Road | East End | High | X:342702 Y:732815 | 6 | Home Group | 30 | [5 empty] | 30 |  |  | 30 | 30 | 27 | 3 |  | 30 | Y | 2017 | [5 empty] | 0 | 30 |  |  |  |  | 30 | 1.482 |  |  |  |  | 1.482
Mill 'O' Mains (phase 4) | East End | High | X:341516 Y:733294 | 5 | Home Group | 40 | [5 empty] | 40 |  |  | 40 | 40 | 34 | 6 | Supported Accommodation | 40 | Y | 2017 | 40 |  |  |  |  | 40 |  | 40 |  |  |  | 40 | 2 | 0.63 |  |  |  | 2.63
Dunbar Park (H33) | North East | High | X:343629 Y:733560 | 5 | Home Group | 24 | [5 empty] | 24 |  |  | 24 | 24 | 22 | 2 | Wheelchair | 24 | Y | 2017 | 24 |  |  |  |  | 24 |  | 24 |  |  |  | 24 | 1.158 |  |  |  |  | 1.158
Candle Lane | Maryfield | Medium | X:340567 Y:730407 | 5 |  | 30 | [5 empty] | 30 |  |  | 30 | 30 | 30 |  |  | 30 | Y | 2018 | 30 |  |  |  |  | 30 |  | 30 |  |  |  | 30 | 1.08 | 1.08 |  |  |  | 2.16
Maryfield House (Mains Loan) | Maryfield | Low | X:340935 Y:731985 | 5 | Sanctuary | 34 |  | 6 |  |  |  | 40 |  |  | 40 | 40 | 34 | 2 | Wheelchair | 36 | Y | 2018 | 40 |  |  |  |  | 40 |  | 40 |  |  |  | 40 | 0.603 | 2.413 |  |  |  | 3.016
Mossgiel Primary School | East End | Medium | X:341778 Y:732628 | 5 | Abertay Housing Association | 42 | [5 empty] | 42 |  |  | 42 | 42 | 42 | TBC | TBC | 42 | Y | 2019 |  | 42 |  |  |  | 42 |  |  | 42 |  |  | 42 |  | 3.024 |  |  |  | 3.024
Longhaugh Road (School Site) | North East | High | X:342893 Y:733313 | 5 | Angus Housing Association | 14 | [5 empty] | 14 |  |  | 14 | 14 | 13 | 1 | Wheelchair | 14 | N | 2019 |  | 14 |  |  |  | 14 |  |  | 14 |  |  | 14 |  | 0.98 |  |  |  | 0.98
Lothian Crescent | North East | High | X:343137 Y:733480 | 5 | Angus Housing Association | 8 | [5 empty] | 8 |  |  | 8 | 8 | 8 |  |  | 8 | N | 2019 |  | 8 |  |  |  | 8 |  | 8 |  |  |  | 8 |  | 0.56 |  |  |  | 0.56
Fettercairn Drive | Barnhill | Low | X:347353 Y:731920 | 5 | Angus Housing Association | 1 | [5 empty] | 1 |  |  | 1 | 1 |  | 1 | Wheelchair | 1 | N | 2018 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1 |  | 0.07 |  |  |  | 0.07
To be Identified |  |  |  | 9 | Dundee City Council | 30 | [5 empty] | 30 |  |  | 30 | 30 | 27 | 3 | Wheelchair | 30 | Y | 2018 |  | 30 |  |  |  | 30 |  |  | 30 |  |  | 30 |  | 1.77 |  |  |  | 1.77
Clepington Road | Maryfield | Medium | X:340923 Y:732161 | 5 | Hillcrest Housing Association | 24 | 12 |  |  |  |  | 36 |  |  | 36 | 36 | 24 | TBC | TBC | 24 | Y | 2018 |  | 36 |  |  |  | 36 |  |  | 36 |  |  | 36 |  | 1.225 | 1.225 |  |  | 2.45
Menzieshill to be identified | Lochee | Medium |  | 5 | Abertay Housing Association | 22 | [5 empty] | 22 |  |  | 22 | 22 | 22 | TBC | TBC | 22 | Y | 2018 |  |  | 22 |  |  | 22 |  |  |  | 22 |  | 22 |  |  | 1.584 |  |  | 1.584
To be Identified |  |  |  | 9 | Dundee City Council | 30 | [5 empty] | 30 |  |  | 30 | 30 | 30 | TBC | TBC | 30 | Y | 2018 |  |  | 30 |  |  | 30 |  |  |  | 30 |  | 30 |  |  | 1.77 |  |  | 1.77
Waterfront | Maryfield | High |  | 5 | To be Identified |  | 60 |  |  |  |  | 60 |  |  | 60 | 60 |  |  |  | 0 | Y | 2018 |  | 30 | 30 |  |  | 60 |  |  | 30 | 30 |  | 60 |  | 1.38 | 1.38 |  |  | 2.76
IB Connex (H62) | Hilltown | High | X:340222 Y:731212 | 5 | To be confirmed | 40 |  |  | 18 |  |  | 58 |  |  | 58 | 58 | 35 | 5 | TBC | 40 | Y | 2018 |  | 58 |  |  |  | 58 |  |  |  | 58 |  | 58 |  | 2.014 | 2.014 |  |  | 4.028
BOC Ballindean Road | East End | Medium | X:343413 Y:732165 | 5 | Hillcrest Housing Association | 25 | [5 empty] | 25 |  |  | 25 | 25 | 20 | 5 | Wheelchair | 25 | Y | 2018 | 25 |  |  |  |  | 25 |  | 25 |  |  |  | 25 | 0.962 | 1 |  |  |  | 1.962
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [7 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [7 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [7 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [7 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [7 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [7 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [7 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [7 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [7 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [7 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [7 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [7 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [7 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [7 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
Total | [5 empty] | 857 | 185 | 6 | 18 | 30 | 0 | 1096 | 0 | 0 | 1096 | 1096 | 736 | 123 | 0 | 859 |  |  | 616 | 267 | 123 | 52 | 8 | 1066 | 152 | 391 | 312 | 181 | 0 | 1036 | 33.472 | 18.793 | 10.284 | 3.506 | 0.401 | 66.456
Drop Down Table Values
[21 empty] | Numerical Value | Geographic Code
[21 empty] | 1 | West Highland/Island Authorities/Remote/Rural Argyll -RSL - SR - Greener |  |  |  |  | RSL - SR - Greener
[21 empty] | 2 | West Highland/Island Authorities/Remote/Rural Argyll |  |  |  |  | RSL - SR - Other
[21 empty] | 3 | Other Rural |  |  |  |  | RSL - SR - Greener
[21 empty] | 4 | Other Rural |  |  |  |  | RSL - SR - Other
[21 empty] | 5 | City and Urban |  |  |  |  | RSL - SR - Greener
[21 empty] | 6 | City and Urban |  |  |  |  | RSL - SR - Other
[21 empty] | 7 | All |  |  |  |  | RSL - Mid-Market Rent - Greener
[21 empty] | 8 | All |  |  |  |  | RSL - Mid-Market Rent - Other
[21 empty] | 9 | All |  |  |  |  | Council - SR - Greener
[21 empty] | 10 | All |  |  |  |  | Council -SR - Other

## TABLE 2 - HIF PROJECTS
MORE HOMES DIVISION
STRATEGIC HOUSING INVESTMENT PLAN 2018/19-2022/23
Table 2 - HOUSING INFRASTRUCTURE FUND (HIF) PROJECTS
Note: Projects should be entered as either Grant or Loan - Any which state a mixed category e.g. Grant/Loan or Grant or Loan will not be considered
TABLE 2.1 - GRANT PROJECTS
[9 empty] | AFFORDABLE HOUSING UNITS DIRECTLY PROVIDED BY INFRASTRUCTURE FUNDING - BY ESTIMATED COMPLETION DATE | [14 empty] | HIF GRANT FUNDING REQUIRED |  |  |  |  | POTENTIAL ADDITIONAL CAPACITY - UNITS NOT DIRECTLY FUNDED BUT UNLOCKED BY INFRASTRUCTURE FUNDING
PROJECT | PRIORITY | GEOGRAPHIC COORDINATES (X:EASTING Y:NORTHING) | APPLICANT | PLANNING STATUS (OUTLINE/ MASTERPLAN/ FULL CONSENT IN PLACE) (Y/N) | DOES APPLICANT OWN OR HAVE POTENTIAL TO OWN THE SITE? (Y/N) | CURRENT SITE OWNER | BRIEF DESCRIPTION OF WORKS FOR WHICH INFRASTRUCTURE FUNDING IS SOUGHT (PROVIDE WORK HEADINGS - DO NOT INSERT "INFRASTRUCTURE WORKS") | IS PROJECT LINKED TO DIRECT PROVISION OF AFFORDABLE HOUSING? (Y/N) | AFFORDABLE |  |  |  |  | MARKET |  |  |  |  | PRIVATE RENT
| Low / Medium / High | [7 empty] | 2018/19 | 2019/20 | 2020/21 | POST 2020/21 | AFFORDABLE TOTAL OVER PLAN OVER SHIP PERIOD | 2018/19 | 2019/20 | 2020/21 | POST 2020/21 | MARKET TOTAL OVER PLAN OVER SHIP PERIOD | 2018/19 | 2019/20 | 2020/21 | POST 2020/21 | PRIVATE RENT TOTAL OVER PLAN OVER SHIP PERIOD | 2018/19 | 2019/20 | 2020/21 | POST 2020/21 | TOTAL HIF GRANT FUNDING REQUIRED | UNITS - POTENTIAL ADDITIONAL CAPACITY IN EITHER LATER PHASES OR OTHER SITES | TENURE - AFFORDABLE / MARKET /PRIVATE RENTED
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Total | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TABLE 2.2 - LOAN PROJECTS
[9 empty] | AFFORDABLE HOUSING UNITS DIRECTLY PROVIDED BY INFRASTRUCTURE FUNDING - BY ESTIMATED COMPLETION DATE | [14 empty] | HIF LOAN FUNDING REQUIRED |  |  |  |  | POTENTIAL ADDITIONAL CAPACITY - UNITS NOT DIRECTLY FUNDED BUT UNLOCKED BY INFRASTRUCTURE FUNDING
PROJECT | PRIORITY | GEOGRAPHIC COORDINATES (X:EASTING Y:NORTHING) | APPLICANT | PLANNING STATUS (OUTLINE/ MASTERPLAN/ FULL CONSENT IN PLACE) (Y/N) | DOES APPLICANT OWN OR HAVE POTENTIAL TO OWN THE SITE? (Y/N) | CURRENT SITE OWNER | BRIEF DESCRIPTION OF WORKS FOR WHICH INFRASTRUCTURE FUNDING IS SOUGHT (PROVIDE WORK HEADINGS - PLEASE "INFRASTRUCTURE WORKS") | IS PROJECT LINKED TO DIRECT PROVISION OF AFFORDABLE HOUSING? (Y/N) | AFFORDABLE |  |  |  |  | MARKET |  |  |  |  | PRIVATE RENT
| Low / Medium / High | [7 empty] | 2018/19 | 2019/20 | 2020/21 | POST 2020/21 | AFFORDABLE TOTAL OVER PLAN OVER SHIP PERIOD | 2018/19 | 2019/20 | 2020/21 | POST 2020/21 | MARKET TOTAL OVER PLAN OVER SHIP PERIOD | 2018/19 | 2019/20 | 2020/21 | POST 2020/21 | PRIVATE RENT TOTAL OVER PLAN OVER SHIP PERIOD | 2018/19 | 2019/20 | 2020/21 | POST 2020/21 | TOTAL HIF LOAN FUNDING REQUIRED | UNITS - POTENTIAL ADDITIONAL CAPACITY IN EITHER LATER PHASES OR OTHER SITES | TENURE - AFFORDABLE / MARKET /PRIVATE RENTED
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Total | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## TABLE 3 - HIF AFFORDABLE HSG
MORE HOMES DIVISION
STRATEGIC HOUSING INVESTMENT PLAN 2018/19-2022/23
Table 3 - POTENTIAL HIF AFFORDABLE HOUSING PROJECTS WHICH MAY BE DEVELOPED FOLLOWING HIF INVESTMENT
LOCAL AUTHORITY:
PROJECT | SUB-AREA | PRIORITY | GEOGRAPHIC COORDINATES (X:EASTING Y:NORTHING) | GEOGRAPHIC CODE (Numeric Value - from Drop Down Table Below) | DEVELOPER | UNITS - TENURE | [6 empty] | UNITS - BUILT FORM |  |  |  | UNITS - TYPE |  |  |  | GREENER STANDARDS | APPROVAL DATE | UNIT SITE STARTS |  |  |  |  | UNITS - COMPLETIONS |  |  |  |  | SG AHSP FUNDING REQUIREMENT (£0.000M)
|  | Low / Medium / High |  |  |  | Social Rent | Mid Market Rent | LCHO - Shared Equity | LCHO - Shared Ownership | LCHO - Improvement for Sale | PSR | Total Units | Rehab | Off the Shelf | NB | Total Units | GN | Specialist Provision | Type of Specialist Particular Need (If Known) | Total Units by Type | Enter Y or N | Financial Year (Estimated or Actual) | 2018/19 | 2019/20 | 2020/21 | POST 2020/21 | TOTAL SITE STARTS OVER PERIOD OF SHIP | 2018/19 | 2019/20 | 2020/21 | POST 2020/21 | TOTAL COMPLETIONS OVER PERIOD OF SHIP | 2018/19 | 2019/20 | 2020/21 | POST 2020/21 | TOTAL AHSP FUNDING REQUIRED OVER SHIP PERIOD
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drop Down Table Values
[21 empty] | Numerical Value | Geographic Code
[21 empty] | 1 | West Highland/Island Authorities/Remote/Rural Argyll -RSL - SR - Greener |  |  |  | RSL - SR - Greener
[21 empty] | 2 | West Highland/Island Authorities/Remote/Rural Argyll |  |  |  | RSL - SR - Other
[21 empty] | 3 | Other Rural |  |  |  | RSL - SR - Greener
[21 empty] | 4 | Other Rural |  |  |  | RSL - SR - Other
[21 empty] | 5 | City and Urban |  |  |  | RSL - SR - Greener
[21 empty] | 6 | City and Urban |  |  |  | RSL - SR - Other
[21 empty] | 7 | All |  |  |  | RSL - Mid-Market Rent - Greener
[21 empty] | 8 | All |  |  |  | RSL - Mid-Market Rent - Other
[21 empty] | 9 | All |  |  |  | Council - SR - Greener
[21 empty] | 10 | All |  |  |  | Council -SR - Other

## TABLE 4 - NON-AHSP PROJECTS
MORE HOMES DIVISION
STRATEGIC HOUSING INVESTMENT PLAN 2018/19-2022/23
LOCAL AUTHORITY:
TABLE 4 - AFFORDABLE HOUSING PROJECTS FUNDED OR SUPPORTED BY SOURCES OTHER THAN THE RPA/TMDF BUDGET
PROJECT ADDRESS | SUB-AREA | PRIORITY | GEOGRAPHIC COORDINATES (X:EASTING Y:NORTHING) | DEVELOPER | FUNDING SUPPORT SOURCE | APPROVAL DATE | [5 empty] | TOTAL | UNIT COMPLETIONS |  |  |  |  | TOTAL UNIT COMPLETIONS | NON SG FUNDING TOTAL £0.000M | OTHER NON-AHSP SG FUNDING (IF APPLICABLE) £0.000M | TOTAL FUNDING £0.000M
|  | Low / Medium / High |  |  |  | Financial Year (Actual or Estimated) | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23 | TOTAL SITE STARTS | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23
[12 empty] | 0 | [5 empty] | 0 |  |  | 0
[12 empty] | 0 | [5 empty] | 0 |  |  | 0
[12 empty] | 0 | [5 empty] | 0 |  |  | 0
[12 empty] | 0 | [5 empty] | 0 |  |  | 0
[12 empty] | 0 | [5 empty] | 0 |  |  | 0
[12 empty] | 0 | [5 empty] | 0 |  |  | 0
[12 empty] | 0 | [5 empty] | 0 |  |  | 0
[12 empty] | 0 | [5 empty] | 0 |  |  | 0
[12 empty] | 0 | [5 empty] | 0 |  |  | 0
[12 empty] | 0 | [5 empty] | 0 |  |  | 0
Total | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Table 5- CT & Developer Cont
MORE HOMES DIVISION
STRATEGIC HOUSING INVESTMENT PLAN 201819-2022/23
LOCAL AUTHORITY:
TABLE 5.1: COUNCIL TAX ON SECOND AND EMPTY HOMES(£0.000M)
| TAX RAISED OR IN HAND | TAX USED TO SUPPORT AFFORDABLE HOUSING | TAX CARRIED FORWARD TO SUBSEQUENT YEARS
PRE - 2015/16
2015/16 | 0.4 |  | 0.4
2016/17 | 0.4 |  | 0.8
TABLE 5.2: DEVELOPER CONTRIBUTIONS (£0.000M)
| SUMS |  |  | UNITS
| RAISED OR IN HAND | USED TO ASSIST HOUSING | SUM CARRIED FORWARD TO SUBSEQUENT YEARS | AFFORDABLE UNITS FULLY FUNDED FROM CONTRIBUTIONS | UNITS PARTIALLY ASSISTED FROM CONTRIBUTIONS | UNITS TOTAL
PRE - 2015/16
2015/16 |  |  | 0 |  |  | 0
2016/17 |  |  | 0 |  |  | 0
Note: These tables are used to capture financial information. Details of how this has been used to fund/assist affordable housing should be contained in the text of the SHIP as described in the guidance.